Project Management Plan

ComiVerse - A Digital Comic Platform with Integrated Translation and Content Distribution Tools

CVP  - Report 2

| Project Name | ComiVerse |
| --- | --- |
| Vision & Scope Ref | Vision & Scope Document v1.1.0 |
| RTW Ref | SEP490_G37_Report 3.1_RTW |
| Plan Version | v1.1.0 |
| Date Created | 22/5/2026 |
| Last Updated | 12/8/2026 |
| Authors | Bùi Quang Hiệp - HE171337 Bùi Việt Hùng - HE163146 Chu Tuấn Ngọc - HE186006 Nguyễn Xuân Hanh - HE180944 Đặng Ngọc Thành - HE186611 |
| Reviewer | Lê Thị Tú Kiên - Instructor |
| Status | Approved |

# 1. Overview

## 1.1 Cost/Time Estimation

| # | Work Package | Est. Effort | Deadline |
| --- | --- | --- | --- |
| Stage 1: Project Initiating (Week 1) |  |  |  |
| 1.1 | Report 1 (Project Introduction) | 3 | Week 2 |
| Stage 2: Project Planning & Initial Requirements (Weeks 2–3) |  |  |  |
| 2.1 | Report 2: Project Management Plan v1.0 | 2 | Week 2 |
| 2.2 | Report 3: SRS v0.9 (Overall Requirement) | 11 | Week 2 |
| 2.3 | Vertical Prototypes (Code Demo) | 10 | Week 3 |
| Stage 3: Software Design (Weeks 4–5) |  |  |  |
| 3.1 | Vertical Prototypes (POC — Proof of Concepts) | 12 | Week 4 |
| 3.2 | Report 4: SDS v1.0 (High-Level Design Specifications) | 10 | Week 4 |
| 3.3 | Report 5: Test Planning | 9 | Week 5 |
| 3.4 | Report 3: SRS v1.0 (Detailed Requirements for Iteration 1) | 8 | Week 5 |
| Stage 4: Implementation (Weeks 6–13) |  |  |  |
| 4.1 Implementation Iteration 1 (Weeks 6–8) |  |  |  |
| 4.1.1 | Report 4: SDS v1.1 (Detailed Design Specifications) | 6 | Week 6 |
| 4.1.2 | Code Package & Unit Testing Report | 25 | Week 6 |
| 4.1.3 | Report 5: Integration Test Cases | 5 | Week 6 |
| 4.1.4 | Report 5: Integration Test Report | 5 | Week 7 |
| 4.1.5 | Report 3: SRS v1.1 (Detailed Requirements for Iteration 2) | 5 | Week 7 |
| 4.1.6 | Software Package Version 1 | 30 | Week 8 |
| 4.2 Implementation Iteration 2 (Weeks 9–11) |  |  |  |
| 4.2.1 | Report 4: SDS v1.2 (Detailed Design Specifications) | 5 | Week 9 |
| 4.2.2 | Code Package & Unit Testing Report | 25 | Week 9 |
| 4.2.3 | Report 5: Integration Test Cases | 5 | Week 10 |
| 4.2.4 | Report 5: Integration Test Report | 5 | Week 10 |
| 4.2.5 | Report 3: SRS v1.2 (Detailed Requirements for Iteration 3) | 5 | Week 11 |
| 4.2.6 | Software Package Version 2 | 30 | Week 11 |
| 4.3 Implementation Iteration 3 (Weeks 12–13) |  |  |  |
| 4.3.1 | Report 4: SDS v1.3 (Detailed Design Specifications) | 5 | Week 12 |
| 4.3.2 | Code Package & Unit Testing Report | 25 | Week 12 |
| 4.3.3 | Report 5: Integration Test Cases | 5 | Week 12 |
| 4.3.4 | Report 5: Integration Test Report | 5 | Week 13 |
| 4.3.5 | Report 5: System Test Cases | 7 | Week 13 |
| 4.3.6 | Software Package Version 3 | 25 | Week 13 |
| Stage 5: Verification & Validation (Weeks 13) |  |  |  |
| 5.1 | Report 5: System Test Report | 8 | Week 13 |
| 5.2 | Report 6: User Guides (Installation Guide, User Manual) | 5 | Week 13 |
| 5.3 | Acceptance Test and Support | 10 | Week 13 |
| 5.4 | Final Software Package (Documents, Source Codes, etc.) | 7 | Week 13 |
| Stage 6: Closing (Week 14) |  |  |  |
| 6.1 | Report 7: Final Project Report | 5 | Week 14 |
| 6.2 | Presentation File | 4 | Week 14 |

## 1.2 Project Objectives

| # | Metric | Unit | Planned | Actual | Notes / References |
| --- | --- | --- | --- | --- | --- |
| 1 | Effort Usage | Person-day | 300 | 400 | Total estimated effort for analysis, development, testing, and deployment |
| 2 | Number of Defect | No. of defects | 15 - 20 | 74 | Includes defects discovered during testing and user acceptance phases |
| 3 | Timeliness | % | 92%-95% | 93% | Percentage of milestones completed on schedule |
| 4 | Requirement Completeness | % | 95% | 95% | Percentage of functional and non-functional requirements successfully implemented |
| 5 | Mobile Application Stability | Crash rate | 3% - 5% | 90% | Stability target for the Android APK application |
| 6 | Performance Response Time | Second | 2-3s | 2-4s | Average loading time for story chapters and forum pages |
| 7 | Forum Moderation Response Time | Hours | <=24 | <=24 | Average response time for handling reported forum content |

## 1.3 Project Risks

| # | Risk Description | Impact | Possibility | Priority | Response Plans (Mitigation / Contingency) |
| --- | --- | --- | --- | --- | --- |
| 1 | Lack of technical skills for Translation Tool | High | High | High | Mitigation: Dedicate the first 2 weeks to researching open-source translation APIs (Google Cloud Translate, DeepL) and NLP models. Build a simple Proof of Concept (PoC) early to test feasibility. Contingency: If custom integration fails, pivot immediately to integrating standard, pre-built third-party APIs to ensure the core feature works on time. |
| 2 | Image processing latency or system crash | High | Medium | High | Mitigation: Design an asynchronous background processing pipeline using Message Queues (e.g., BullMQ, RabbitMQ) and enforce automatic image conversion to WebP format upon upload. Contingency: Implement CDN caching (e.g., Cloudflare, Cloudinary) to offload the main server and provision temporary cloud storage scaling if server load peaks during testing. |
| 3 | Work progress is slow | High | Medium | High | Mitigation: Breakdown tasks into granular sub-tasks on Jira/Trello with strict 3-day deadlines. Hold short status sync meetings 3 times a week. Contingency: Re-allocate secondary non-core tasks to later phases and authorize "crunch time" (overtime coding sessions) to secure critical project milestones. |
| 4 | Requirement changes or scope creep | Medium | High | Medium | Mitigation: Maintain weekly sync-ups with the supervisor to sign off on requirements. Document all agreed features in the SRS and strictly avoid adding "nice-to-have" features. Contingency: If new requirements are requested late, negotiate with the supervisor to push them into the "Future Development" section to protect the current scope. |
| 5 | Conflict or lack of communication within the team | High | Low | Medium | Mitigation: Establish a clear team working agreement, transparent task assignments on the Kanban board, and fixed communication channels (Slack/Discord). Contingency: The team leader will immediately step in to mediate conflicts. If a member is incapacitated, their core tasks will be redistributed among remaining members to secure project delivery. |

# 2. Management Approach

## 2.1 Project Processes

This project follows the Agile Scrum development methodology. The system is developed through multiple sprints, allowing the team to continuously improve features, gather feedback, and adapt to requirement changes throughout the project lifecycle.

Scope Management

Project scope is managed through a prioritized product backlog containing functional and non-functional requirements. Features are selected and refined during sprint planning meetings to ensure the project remains aligned with timeline and resource constraints.

Change Management

Requirement changes are documented and evaluated before implementation. Major changes affecting architecture, database design, or sprint objectives require team discussion and approval to minimize project risks and scope creep.

Time Management

The project timeline is divided into multiple development sprints. Each sprint includes:

- Requirement analysis

- Feature implementation

- Testing

- Review and retrospective

Progress is monitored weekly using task tracking tools such as GitHub Projects

Issue Management

Project issues, bugs, and blockers are tracked using an issue management system. Issues are categorized by priority level (Critical, Major, Minor) and assigned to responsible team members for resolution.

## 2.2 Quality Management

The project applies several quality assurance activities to improve software reliability, maintainability, and overall system stability throughout development.

### Defect Prevention

Coding guidelines and architectural conventions are established early in development to reduce common implementation errors and maintain consistency across services.

### Peer Reviews

Code changes are reviewed by team members through pull requests before merging into the main branch. Peer reviews help identify logic issues, improve code readability, and enforce development standards.

### Unit Testing

Core business logic and API endpoints are validated through unit testing to ensure expected behavior under different conditions.

### Integration Testing

Integration testing is conducted to verify communication between system components such as authentication, chapter management, payment, and forum services.

### Code Standards

The project follows standardized naming conventions, modular architecture principles, and clean code practices to improve maintainability and scalability.

### Version Control

Git and GitHub are used for source code management, collaboration, and change tracking across development branches.

## 2.3 Project Training Plan

| Training Area | Participants | When / Duration |
| --- | --- | --- |
| Java Spring Boot Fundamentals | Entire Team | Week 4 – 2 weeks |
| React.js Fundamentals | Entire Team | Week 4 – 2 weeks |
| Git & GitHub Workflow | Entire Team | Week 4 – 3 days |
| Database Design & SQL | Entire Team | Week 4 – 1 week |
| JWT Authentication & Authorization | Entire Team | Week 6 – 1 week |
| Docker & Containerization | Entire Team | Week 6 – 3 days |
| WebSocket Communication | Assigned Feature Members | Week 6 – 3 days |
| UI/UX Design Principles | Entire Team | Throughout project |
| Agile Scrum Practices | Entire Team | Throughout project |
| Testing & Debugging Techniques | Entire Team | Throughout project |

# 3. Responsibility Assignments

| Work Package | HiepBQ | TuanCN | ThanhDN | HanhNX | HungBV |
| --- | --- | --- | --- | --- | --- |
| Requirement Analysis | A | R | R | I | I |
| UI/UX Design | I | A | R | R | I |
| Frontend Development | R | R | A | I | R |
| Backend Development | R | I | R | A | R |
| Database Design | I | R | I | A | R |
| Testing & Bug Fixing | R | R | I | R | A |
| Documentation | A | R | I | R | R |
| Deployment & Hosting | R | I | R | R | A |

# 4. Project Communications

| Communication Item | Who / Target | Owner | Purpose | When / Frequency | Type / Tool |
| --- | --- | --- | --- | --- | --- |
| Daily Meeting | All Team Members | All Team Members | Update daily progress, discuss blockers, assign urgent tasks | Every day - 15 minutes | Google Meet |
| Weekly Meeting | Entire Project Team + Instructor | All Team Members | Review weekly progress, evaluate completed tasks, plan next sprint | Every Saturday evening | Google Meet |
| Requirement Discussion | All Team Members | All Team Members | Clarify feature requirements and system workflows | When new feature is proposed | Google Meet / Figma |
| Bug Review Meeting | Developers | All Team Members | Review critical bugs and prioritize fixes | Twice per week | Google Meet |
| Progress Reporting | All Members | All Team Members | Report completed tasks and current work status | End of each working day | Google Sheets / Messenger |

# 5. Configuration Management

## 5.1 Document Management

All project documents are managed in a centralized Google Drive folder to ensure consistency, version control, and accessibility for all team members. The project uses Google Docs, Google Sheets, and Google Slides for documentation, planning, reporting, and presentation materials. These tools are also listed as the main documentation tools of the project .

### Document Naming Convention

Each project document must follow a consistent naming format:

SEP490_G37_[Document Type][Version]

Example:

- SEP490_G37_Report 2_Project_Plan_v1.0

- SEP490_G37_Report 2.1_Project_Tracking_v 1.0.0

This naming convention helps the team identify the project name, document type, version, and update time quickly.

### Version Control

Each major document must include version information, last updated date, author, reviewer, and status. For example, the current Project Management Plan includes version, created date, last updated date, authors, reviewer, and review status .

Document versions are managed using the following rules:

| Version Type | Meaning |
| --- | --- |
| v0.x | Draft version under development |
| v1.0 | First official reviewed version |
| v1.x | Updated version after changes or feedback |
| v2.0 | Major revision after important scope or structure changes |

When a document is updated, the editor must record the change in the document history or change log, including the updated section, reason for change, date, and editor name.

### Storage Location

All official documents are stored in the team’s shared Google Drive folder. Supporting files such as diagrams, spreadsheets, meeting notes, and presentation files are also stored in the same folder structure.

Only the latest approved version should be placed in the main folder. Older versions should be moved to the Archive folder to avoid confusion.

### Access Control

Document access is controlled based on team roles:

| Role | Access Permission |
| --- | --- |
| Team Leader | Full access: create, edit, review, approve |
| Team Members | Edit assigned documents and comment on others |
| Instructor / Reviewer | View and comment |
| External Users | No access unless approved by Team Leader |

The Team Leader is responsible for managing access permissions, checking document completeness, and ensuring that submitted documents are the correct version.

### Document Review and Approval

Before submission, each document must be reviewed by at least one team member or the Team Leader. The review process checks:

- Correct format and naming convention

- Accurate version number

- Complete required sections

- Consistency with project scope and requirements

- No duplicated or outdated content

After review, the document status can be updated from Draft to In Review, and finally to Approved when it is ready for submission.

## 5.2 Source Code Management

All project source code is managed using Git and GitHub. GitHub is used as the central repository for storing source code, tracking changes, managing development branches, reviewing code, and coordinating integration among team members.

### 1. Branching Strategy

The project follows a simplified feature-branch workflow.

| Branch | Purpose |
| --- | --- |
| main | Contains the stable and approved source code. Only reviewed and tested code may be merged into this branch. |
| develop | Integration branch used to combine completed features before they are released to main. |
| feature/<feature-name> | Used by developers when implementing a new feature or module. |
| fix/<issue-name> | Used for fixing functional defects or implementation problems. |
| hotfix/<issue-name> | Used for urgent fixes affecting the stable version. |

Developers must create a separate branch for each assigned feature or bug instead of implementing changes directly on the main branch.

Example:

feature/translator-payout

feature/comic-management

fix/chapter-upload-validation

hotfix/payment-error

After the assigned work is completed and tested, the developer creates a Pull Request to merge the changes into the appropriate integration branch.

### 2. Commit Convention

Commit messages must clearly describe the purpose of each change. The project uses the following convention:

<type>: <short description>

Common commit types include:

| Type | Purpose |
| --- | --- |
| feat | Add a new feature |
| fix | Fix a bug or incorrect behavior |
| refactor | Improve code structure without changing functionality |
| test | Add or update test cases |
| docs | Update documentation |
| style | Change formatting or code style |
| chore | Maintenance or configuration changes |

Examples:

feat: add translator payout request

fix: validate duplicate chapter upload

refactor: simplify comic moderation service

test: add unit tests for payment service

docs: update API documentation

Commits should be small and focused on one logical change. Developers should avoid combining unrelated features or bug fixes in the same commit.

### 3. Pull Request and Code Review Process

Code changes must be reviewed through GitHub Pull Requests before being merged into the shared development branches. This supports the project's peer-review and quality-management process.

The code review process is:

- The developer completes the assigned implementation and performs local testing.

- The developer pushes the working branch to GitHub.

- A Pull Request is created with a clear description of the implemented feature, affected modules, and relevant issue or task.

- At least one other team member reviews the code.

- The reviewer checks logic correctness, coding conventions, security, possible side effects, and compatibility with existing modules.

- If issues are detected, the developer updates the same branch and Pull Request.

- The Pull Request may be merged only after required corrections are completed and the code is considered stable.

Direct commits to main should be avoided. Critical changes affecting shared entities, database structures, authentication, payment, or common components must receive additional review because they may affect multiple modules.

### 4. Issue and Change Traceability

Bugs, implementation tasks, and blockers are tracked through GitHub issues and project-management functions. The existing project process already categorizes issues by priority and assigns them to responsible members.

Where applicable, commits and Pull Requests should reference the corresponding issue or task so that source-code changes can be traced back to the work item.

Example:

fix: correct translator revenue calculation (#125)

This process ensures that source code changes remain traceable, reviewable, and recoverable throughout all project iterations.

## 5.3 Tools & Infrastructure

| Category | Tools / Infrastructure |
| --- | --- |
| Technology | React (Front-End), Flutter(App), Java / Spring Boot (Back-End) |
| Database | PostgreSQL 16 , Firebase |
| IDEs / Editors | Intelij, Android studio, WebStorm |
| Diagramming | draw.io |
| Documentation | MS Office, Google Docs / Sheets / Slides |
| Version Control | GitHub (Source Codes), Google Drive (Documents) |
| Deployment Server | Railway |
| Project Management | GitHub (tasks, time logs, defects, issues) |