## Summary
REPORT 5.3 — SYSTEM TESTS LEVEL 3
Project | ComiVerse — Digital Comic Platform
Scope | Backend + Frontend Level 3 System Tests (Functional & Non-Functional)
Source code | SEP490_G37_SUM26_JAVA & ComiVerse_FE
Test result source | API: Postman / MockMvc; E2E UI: Playwright / Manual; Performance: JMeter / DevTools
Report basis | 1 row per System Test Scenario / Business Flow Execution
Generated on | 2026-08-03
No. | Test Class / File | Layer | BF/NFR/BR Coverage | Designed Cases | Executed Invocations | Pass | Fail | Skip/Blocked | Status | Sheet
1 | HTTPFlows | Multi-step HTTP API Flows | BF-03, BF-04 | 9 | 9 | 9 | 0 | 0 | Pass | Verified via Postman/MockMvc (Includes DEF-029 Fixed)
2 | E2E_BF | End-to-End Browser Flows | BF-01, BF-03, BF-04, BF-05, BF-06, BF-08 | 63 | 63 | 63 | 0 | 0 | Pass | Verified via Playwright (Includes DEF-033 Fixed)
3 | Security_SpotChecks | System-Wide Backend Security | NFR-23, NFR-24, BR-03, BR-60, BR-76, BR-100, BR-108, BR-109, BR-110 | 9 | 9 | 9 | 0 | 0 | Pass | Verified via MockMvc (Includes DEF-030, DEF-031, DEF-032 Fixed)
4 | Performance | Backend Load & UI Metrics | NFR-01, NFR-09, NFR-13, NFR-18, NFR-19 | 5 | 5 | 5 | 0 | 0 | Pass | Verified via Chrome DevTools
TOTAL | 10 Components | All System Layers | 8 BFs + NFRs | 86 | 86 | 86 | 0 | 0 | Pass | 100% Execution Rate, 0 Active Defects

## HTTPFlows
Test Case ID | BF-ID / Flow Name | Step No. | Actor / Role | Action (When) | Expected Result (Then) | Tool | Priority | Status | Defect ID | Notes
TC-SYS-BF04-001 | BF-04 Comic Publishing & Moderation | 1 | Author | POST /comics with JSON payload | Returns 201 Created; DB saves Comic with status SUBMITTED_FOR_REVIEW | MockMvc / Java | Critical | Pass |  | Initial comic payload
TC-SYS-BF04-002 | BF-04 Comic Publishing & Moderation | 2 | Author | POST /chapters with Chapter metadata | Returns 201 Created; DB saves Chapter with status PENDING_REVIEW | MockMvc / Java | Critical | Pass |  | Chapter info setup
TC-SYS-BF04-003 | BF-04 Comic Publishing & Moderation | 3 | Moderator | GET /submissions/all with valid JWT | Returns 200 OK; JSON list contains the newly created pending submission | MockMvc / Java | Critical | Pass |  | Fetch review queue
TC-SYS-BF04-004 | BF-04 Comic Publishing & Moderation | 4 | Moderator | PUT /submissions/{id}/approve | Returns 200 OK; DB updates Comic & Chapter status to PUBLISHED | MockMvc / Java | Critical | Pass |  | Moderator approves
TC-SYS-BF04-005 | BF-04 Comic Publishing & Moderation | 5 | Reader | GET /comics/{id} | Returns 200 OK; Comic details returned since it is now published | MockMvc / Java | Critical | Pass |  | Public discovery
TC-SYS-BF04-006 | BF-04 Comic Publishing & Moderation | - | Moderator | PUT /submissions/{id}/reject with reason | Returns 200 OK; Chapter images tombstoned to save space; status = REJECTED | MockMvc / Java | High | Pass | DEF-029 | Previously threw 500 error on rejection cleanup. Fixed.
TC-SYS-BF03-001 | BF-03 Translation Project Management | 1 | Translator | POST /translator-registration | Returns 201 Created; User role elevated to TRANSLATOR in DB | MockMvc / Java | Critical | Pass |  | Role elevation
TC-SYS-BF03-002 | BF-03 Translation Project Management | 2 | Moderator | POST /translation-pool/request | Returns 200 OK; ProjectTeamEntity created with status UNCLAIMED | MockMvc / Java | Critical | Pass |  | Unclaimed pool setup
TC-SYS-BF03-003 | BF-03 Translation Project Management | 3 | Translator | PUT /translation-pool/{id}/claim | Returns 200 OK; Project team becomes ACTIVE; Leader assigned | MockMvc / Java | Critical | Pass |  | Claiming workspace

## E2E_BF
Test Case ID | BF-ID / Flow Name | Step No. | Actor / Role | Action (When — browser interaction) | Expected Result (Then — UI) | Tool | Priority | Status | Defect ID | Notes
TC-E2E-BF04-001 | BF-04 Comic Publishing & Moderation | 1 | Author | Open /auth, log in as author, navigate to /author/comics, fill title "Cyber Saga" & summary, click "Create Draft" | Draft comic created (moderationStatus = DRAFT); displayed in author comic list | Playwright | Critical | Pass |  | Initial draft creation
TC-E2E-BF04-002 | BF-04 Comic Publishing & Moderation | 2 | Author | Click "Upload Chapter", attach chapter folder archive (.zip / images), click "Submit Upload" | Upload progress reaches 100%; toast "12 files uploaded"; chapter status set to "DRAFT" | Playwright | Critical | Pass |  | Chapter payload upload
TC-E2E-BF04-003 | BF-04 Comic Publishing & Moderation | 3 | Author | Click "Submit for Review" button on draft comic toolbar | Status updates to PENDING_REVIEW; submit button turns disabled | Playwright | Critical | Pass |  | Submission to Moderator
TC-E2E-BF04-004 | BF-04 Comic Publishing & Moderation | 4 | Moderator | Switch session to Moderator, open /moderator/submissions, click "Approve" on "Cyber Saga" | Submission status updates to PUBLISHED; comic becomes visible on public storefront | Playwright | Critical | Pass |  | Moderator approval flow
TC-E2E-BF04-005 | BF-04 Comic Publishing & Moderation | 5 | Moderator | Open review modal for invalid submission, enter reason "Low image resolution", click "Reject" | Submission status updates to REJECTED; feedback reason logged | Playwright | High | Pass |  | Rejection flow
TC-E2E-BF04-006 | BF-04 Comic Publishing & Moderation | 6 | Author | View rejection reason on author dashboard, update cover resolution, click "Resubmit Review" | New submission ticket created (sub-resubmit-002); status returns to PENDING_REVIEW | Playwright | High | Pass |  | Re-submission cycle
TC-E2E-BF03-001 | BF-03 Translation Project Management | 1 | Moderator | Navigate to /moderator/project-teams, click "Create Team", assign comic "Cyber Saga" & Project Leader | Translation Team created; displayed under active teams with Leader badge | Playwright | Critical | Pass |  | Team initialization
TC-E2E-BF03-002 | BF-03 Translation Project Management | 2 | Translator | Log in as Translator, navigate to /translator/projects, click "Apply to Join Team" | Join request submitted (status = PENDING); pending badge shown on Leader desk | Playwright | High | Pass |  | Team application
TC-E2E-BF03-004 | BF-03 Translation Project Management | 4 | Project Leader | Open /translator/workspace, click "Create Task", select Chapter 1, assign to Translator | Task created (task-101-202) with status BACKLOG / assigned to translator | Playwright | Critical | Pass |  | Task assignment
TC-E2E-BF03-005 | BF-03 Translation Project Management | 5 | Translator | Open workspace canvas /translator/workspace/task-101, edit translated text layers, click "Save Progress" | Canvas updates with translated pages; toast "Progress saved successfully" | Playwright | Critical | Pass | DEF-033 | Threw CORS error on canvas save originally. Fixed reverse proxy config.
TC-E2E-BF06-001 | BF-06 Payment & Revenue Management | 1 | Reader | Log in as Reader, open search bar, type "Cyber Saga", click comic details card | Comic details page loads displaying view count, rating, and chapter list | Playwright | High | Pass |  | Catalog navigation
TC-E2E-BF06-003 | BF-06 Payment & Revenue Management | 3 | Reader | Click Chapter 5 (Locked Premium Chapter / 50 Coins) with balance = 0 | Paywall modal triggers: "Requires 50 Coins. Balance: 0 Coins", displays "Top Up" button | Playwright | Critical | Pass |  | Paywall trigger
TC-E2E-BF06-004 | BF-06 Payment & Revenue Management | 4 | Reader | Click "Top Up", select "500 Coins Pack ($4.99)", complete sandbox card checkout | Transaction succeeds; balance updates to 500 Coins; toast "500 Coins added" | Playwright | Critical | Pass |  | Coin top-up payment
TC-E2E-BF06-005 | BF-06 Payment & Revenue Management | 5 | Reader | Return to Chapter 5 modal, click "Confirm Unlock (50 Coins)" | 50 Coins deducted; balance updates to 450 Coins; chapter access granted | Playwright | Critical | Pass |  | Chapter unlock deduction
TC-E2E-BF01-001 | BF-01 User Authentication & Profile Management | 1 | Guest | Open /auth?mode=register, enter username, email, password, click "Register" | Registration request succeeds; toast "Verification code sent to your email" | Playwright | Critical | Pass |  | Account registration
TC-E2E-BF05-001 | BF-05 Community Interaction & Compliance | 1 | Moderator | Issue Warning Strike 1 against violating user target_spammer | Penalty calculated: 1st Strike = 1-Hour Chat Mute (penaltyType = MUTE) | Playwright | Critical | Pass |  | Graduated strike enforcement
TC-E2E-BF08-002 | BF-08 Platform Administration | 2 | Admin | Search violating_user in user management table, click "Ban User", confirm ban | Status badge changes to BANNED; user blocked from logging into system | Playwright | Critical | Pass |  | Account ban enforcement
TC-E2E-BF01-001 | BF-01 User Authentication & Profile Management | 1 | Guest | Open /auth, navigate to Register tab, enter valid username, email, password, and click "Create Account" | Toast "Verification code sent to email" appears; UI transitions to 6-digit OTP verification screen | Vitest / Playwright | Critical | Passed | — | Happy path user registration
TC-E2E-BF01-002 | BF-01 User Authentication & Profile Management | 2 | Guest | Enter valid 6-digit OTP code on verification screen and click "Verify Email" | Toast "Email verified successfully"; form switches to Login tab with email prefilled | Vitest / Playwright | Critical | Passed | — | OTP email verification
TC-E2E-BF01-003 | BF-01 User Authentication & Profile Management | 3 | Reader | Open /auth, enter username/password for Reader account, and click "Sign In" | Redirects to /; top navigation bar displays user avatar, username, coin balance, and notification bell | Vitest / Playwright | Critical | Passed | — | Authentication & session creation
TC-E2E-BF01-004 | BF-01 User Authentication & Profile Management | 4 | Reader | Navigate to /profile, edit display name and biography, then click "Save Changes" | Toast "Profile updated successfully"; updated display name and bio reflect immediately on UI | Vitest / Playwright | High | Passed | — | Profile data management
TC-E2E-BF01-005 | BF-01 User Authentication & Profile Management | 5 | Reader | Go to Security tab in /profile, enter current password and new valid password, click "Change Password" | Toast "Password changed successfully"; password input fields are cleared | Vitest / Playwright | High | Passed | — | Password change workflow
TC-E2E-BF02-001 | BF-02 Comic Discovery & Reading | 1 | Reader | Type comic title keyword (e.g., "Solo") in search bar and press Enter | Redirects to /search or /comics; grid displays matching comic cards with titles, covers, and genre badges | Vitest / Playwright | High | Passed | — | Keyword search
TC-E2E-BF02-002 | BF-02 Comic Discovery & Reading | 2 | Reader | Open /ranking, click on "Top Rating" leaderboard tab | Leaderboard renders top-ranked comics sorted by rating with rank medals (1st, 2nd, 3rd) and view counts | Vitest / Playwright | Medium | Passed | — | Ranking leaderboard
TC-E2E-BF02-003 | BF-02 Comic Discovery & Reading | 3 | Reader | Click on comic card to open /comic/{id} | Comic detail renders cover, synopsis, author, rating score, and full chapter list | Vitest / Playwright | Critical | Passed | — | Comic details & chapter table
TC-E2E-BF02-004 | BF-02 Comic Discovery & Reading | 4 | Reader | On /comic/{id}, click "Bookmark / Add to Library" button | Button state changes to "Bookmarked" (saved state); comic is added to reader's /library page | Vitest / Playwright | High | Passed | — | Library save / bookmark toggle
TC-E2E-BF02-005 | BF-02 Comic Discovery & Reading | 5 | Reader | Click on Chapter 1 to open /comic/{id}/chapter/{chapterId} | Chapter viewer loads canvas/images in reading order; scroll mode controls work; reading progress is recorded | Vitest / Playwright | Critical | Passed | — | Chapter viewer & reading progress
TC-E2E-BF03-001 | BF-03 Translation Project Management | 1 | Project Leader | Navigate to /translator/project-teams, click "Create Team", select comic & target language, click "Create" | New project team card appears in active teams list with status "ACTIVE" | Vitest / Playwright | Critical | Passed | — | Team initialization
TC-E2E-BF03-002 | BF-03 Translation Project Management | 2 | Translator | Open /translator/project-list, find team and click "Request to Join", submit note | Button state changes to "Request Sent (Pending)"; request appears in team leader queue | Vitest / Playwright | High | Passed | — | Join team request
TC-E2E-BF03-003 | BF-03 Translation Project Management | 3 | Project Leader | In team Requests tab, click "Approve" on pending translator request | Translator is added to the Team Roster; request status updates to "APPROVED" | Vitest / Playwright | High | Passed | — | Leader approval of member
TC-E2E-BF03-004 | BF-03 Translation Project Management | 4 | Project Leader | In Tasks tab, click "Assign Task", select Chapter 1 and assignee, click "Assign" | Task card is created in Kanban board with status "ASSIGNED" / "IN_PROGRESS" | Vitest / Playwright | Critical | Passed | — | Translation task assignment
TC-E2E-BF03-005 | BF-03 Translation Project Management | 5 | Translator | Open /translator/translate-workspace/task/{id}, edit speech bubble texts, click "Save Draft" | Toast "Draft saved successfully"; text bubble translations and canvas state persist | Vitest / Playwright | Critical | Passed | — | Translate workspace editing
TC-E2E-BF03-006 | BF-03 Translation Project Management | 6 | Translator | In translation workspace, click "Submit for Review" | Task status transitions to "IN_REVIEW"; QA notification sent to Project Leader | Vitest / Playwright | High | Passed | — | Task submission for QA
TC-E2E-BF03-007 | BF-03 Translation Project Management | 7 | Project Leader | Open /translator/review-workspace/task/{id}, inspect pages, click "Approve Chapter" | Task status changes to "APPROVED"; localized chapter is packaged for moderation review | Vitest / Playwright | Critical | Passed | — | Review workspace QA approval
TC-E2E-BF04-001 | BF-04 Comic Publishing & Moderation | 1 | Author | Open /author/comics, click "New Comic", enter title, synopsis, genres, upload cover, click "Create" | New comic card created with status "DRAFT" in Author Comics dashboard | Vitest / Playwright | Critical | Passed | — | Author draft creation
TC-E2E-BF04-002 | BF-04 Comic Publishing & Moderation | 2 | Author | On /author/comics/{id}, click "Add Chapter", upload chapter image folder, click "Upload" | Upload progress completes 100%; chapter is added to chapters list with total page count | Vitest / Playwright | Critical | Passed | — | Chapter folder upload
TC-E2E-BF04-003 | BF-04 Comic Publishing & Moderation | 3 | Author | Click "Submit for Review" on draft chapter | Confirmation dialog accepted; chapter moderation status updates from "DRAFT" to "PENDING" | Vitest / Playwright | Critical | Passed | — | Submission to moderation
TC-E2E-BF04-004 | BF-04 Comic Publishing & Moderation | 4 | Moderator | Open /moderator Review Queue, select pending chapter, click "Approve Submission" | Toast "Chapter approved and published"; status updates to "PUBLISHED"; visible on public reader | Vitest / Playwright | Critical | Passed | — | Moderator approval
TC-E2E-BF04-005 | BF-04 Comic Publishing & Moderation | 5 | Moderator | In Review Queue, click "Reject Submission", enter feedback reason, click "Confirm Reject" | Submission status updates to "REJECTED"; feedback reason is recorded and attached | Vitest / Playwright | High | Passed | — | Moderator rejection with reason
TC-E2E-BF04-006 | BF-04 Comic Publishing & Moderation | 6 | Author | On /author/comics/{id}, view rejection feedback, fix issues, and click "Resubmit Review" | Chapter status returns to "PENDING" in review queue | Vitest / Playwright | High | Passed | — | Rejection feedback & resubmission
TC-E2E-BF05-001 | BF-05 Community Interaction & Compliance | 1 | Reader | Scroll to Comments on /comic/{id}, type comment content, click "Post Comment" | Comment is published and rendered in comment stream with user avatar and timestamp | Vitest / Playwright | High | Passed | — | Public comic comment
TC-E2E-BF05-002 | BF-05 Community Interaction & Compliance | 2 | Reader | Open /forum, click "New Thread", enter title, category, and body, click "Publish Thread" | Thread appears on Forum list; redirects to /forum/thread/{id} | Vitest / Playwright | High | Passed | — | Forum thread creation
TC-E2E-BF05-003 | BF-05 Community Interaction & Compliance | 3 | User | Click "Report" flag on offensive comment, select reason category, enter details, click "Submit" | Toast "Report submitted to moderation team"; report record is registered in moderation backend | Vitest / Playwright | High | Passed | — | Report violation modal
TC-E2E-BF05-004 | BF-05 Community Interaction & Compliance | 4 | Moderator | Open /moderator/reports, select pending report, enter resolution note, click "Accept Report" | Report status changes to "RESOLVED"; offending content is hidden/removed | Vitest / Playwright | Critical | Passed | — | Report resolution action
TC-E2E-BF05-005 | BF-05 Community Interaction & Compliance | 5 | Moderator | Select repeat offender user, trigger "Issue Strike 1" penalty | User receives 1st Warning Strike (1-Hour Chat Mute); restriction persists in state | Vitest / Playwright | High | Passed | — | Graduated warning penalty
TC-E2E-BF05-006 | BF-05 Community Interaction & Compliance | 6 | User | User logs in and checks notification dropdown | Notification bell displays "⚠️ 1st Warning Strike — Muted for 1 Hour" alert message | Vitest / Playwright | High | Passed | — | Compliance alert delivery
TC-E2E-BF05-007 | BF-05 Community Interaction & Compliance | 7 | Admin | Open /admin/broadcast, enter title, message, target audience "ALL", click "Broadcast" | Toast "Broadcast published successfully"; announcement banner is sent to all connected users | Vitest / Playwright | High | Passed | — | Platform broadcast notice
TC-E2E-BF06-001 | BF-06 Payment & Revenue Management | 1 | Reader | Click "Get Coins", select "1000 Coins ($9.99)", complete sandbox payment checkout | Redirects to /subscription/success; reader wallet coin balance updates to +1000 coins | Vitest / Playwright | Critical | Passed | — | Coin top-up checkout
TC-E2E-BF06-002 | BF-06 Payment & Revenue Management | 2 | Reader | Open locked Chapter 5 (50 Coins), click "Confirm Unlock" | 50 Coins deducted; wallet balance reflects remaining coins; chapter unlocks immediately | Vitest / Playwright | Critical | Passed | — | Premium chapter paywall unlock
TC-E2E-BF06-003 | BF-06 Payment & Revenue Management | 3 | Creator | Open /author/payout or /translator/payout, enter withdrawal amount $150, click "Request Payout" | Toast "Payout request submitted"; transaction status displays as "PENDING" in payout history | Vitest / Playwright | Critical | Passed | — | Creator payout request
TC-E2E-BF06-004 | BF-06 Payment & Revenue Management | 4 | Admin | Open /admin/payout, select pending $150 payout, enter note, click "Approve Payout" | Payout status updates to "APPROVED"; transfer receipt timestamp is logged | Vitest / Playwright | Critical | Passed | — | Admin payout approval
TC-E2E-BF07-001 | BF-07 Analytics & Reporting | 1 | Author | Open /author/overview, select date range "Last 30 Days" | Dashboard displays Total Views, Followers Growth, Chapter Retention Rate, and Revenue graphs | Vitest / Playwright | High | Passed | — | Author analytics dashboard
TC-E2E-BF07-002 | BF-07 Analytics & Reporting | 2 | Project Leader | Open /leader/reports, select project team | Team report renders translation velocity, completed chapters count, and translator contributions | Vitest / Playwright | High | Passed | — | Translation team productivity
TC-E2E-BF07-003 | BF-07 Analytics & Reporting | 3 | Admin | Open /admin/statistics overview | Dashboard renders Total Users, Daily Active Readers, Platform Revenue, and Published Comics | Vitest / Playwright | High | Passed | — | Platform admin statistics
TC-E2E-BF08-001 | BF-08 Platform Administration | 1 | Admin | Open /admin/account-management, click "Add Staff", fill username, email, role "MODERATOR", click "Save" | New moderator account appears in Staff Accounts table with status "ACTIVE" | Vitest / Playwright | Critical | Passed | — | Staff account registration
TC-E2E-BF08-002 | BF-08 Platform Administration | 2 | Admin | Search violating user in /admin/account-management, click "Ban User", enter reason, click "Confirm" | User status badge changes to "BANNED"; user sessions are revoked | Vitest / Playwright | Critical | Passed | — | User ban enforcement
TC-E2E-BF08-003 | BF-08 Platform Administration | 3 | Admin | Filter by "BANNED" users, click "Unban User" on rehabilitated account | User status badge changes back to "ACTIVE"; account access is restored | Vitest / Playwright | High | Passed | — | User account unban
TC-E2E-BF08-004 | BF-08 Platform Administration | 4 | Admin | Open /admin/settings, adjust Max Upload Size to 50MB and toggle Maintenance Mode, click "Save" | Toast "System settings updated successfully"; new system configuration persists | Vitest / Playwright | High | Passed | — | Admin system settings
TC-E2E-BF08-005 | BF-08 Platform Administration | 5 | Admin | Open /admin/report-categories, click "Add Category", enter name "Copyright Infringement", click "Save" | New category appears in report category table and becomes selectable in reader report modal | Vitest / Playwright | High | Passed | — | Report category management
TC-E2E-RBAC-001 | Security spot-check (UI) | — | Reader | Log in as Reader, attempt direct URL navigation to /admin/statistics | Access is denied; user is blocked and redirected away from Admin dashboard | Vitest / Playwright | Critical | Passed | — | RBAC: Reader blocked from Admin
TC-E2E-RBAC-002 | Security spot-check (UI) | — | Reader | Log in as Reader, attempt direct URL navigation to /moderator | Access is denied; user is blocked and redirected away from Moderator dashboard | Vitest / Playwright | Critical | Passed | — | RBAC: Reader blocked from Moderator
TC-E2E-RBAC-003 | Security spot-check (UI) | — | Author | Log in as Author, attempt direct URL navigation to /translator/translate-workspace/task/{id} | Access is denied; user is blocked and redirected away from Translator workspace | Vitest / Playwright | High | Passed | — | RBAC: Author blocked from Translator
TC-E2E-SESSION-001 | Session management | — | Reader | Log in, click "Sign Out", then click the browser "Back" button | User cannot access authenticated pages; session tokens in localStorage are purged; redirects to /auth or / | Vitest / Playwright | High | Passed | — | Session invalidation on sign-out

## Security_SpotChecks
Test Case ID | GBR-ID / NFR-SEC-ID | Scenario Name | Role / Session | Given | When | Then (Expected) | Priority | Status | Defect ID | Notes
TC-SYSSEC-001 | NFR-23 | File Upload Mime-Type Sniffing Prevention | Authenticated | File upload endpoint open | Attempt to upload .php file disguised as .png | HTTP 5xx Server Error or 403 Forbidden; Cloudinary / File Server rejects it | Critical | Pass | DEF-031 | Verified via MockMvc Java test
TC-SYSSEC-002 | BR-108 | Cross-Origin Resource Sharing (CORS) Policy | Guest | Frontend hosted on Vercel | API requested from http://evil-site.com Origin | HTTP 403 Forbidden; browser blocks CORS response | Critical | Pass |  | Verified via MockMvc Java test
TC-SYSSEC-003 | BR-109 | Global Exception Handler Data Leakage | Guest | API Endpoint expecting JSON | Send severely malformed JSON payload (broken {}) | HTTP 500 / 400 with NO stackTrace or Java classes in response | High | Pass | DEF-030 | Verified via MockMvc Java test
TC-SYSSEC-004 | BR-110 | Actuator Endpoint Protection | Guest | Application running | Call GET /actuator/env or /actuator/heapdump | HTTP 401 Unauthorized or 404 Not Found | High | Pass |  | Verified via MockMvc Java test
TC-SYSSEC-005 | NFR-24 | DDoS Rate Limiting Protection | Guest | Public API | Send 60 requests in 1 minute to /comics/explore | HTTP 429 Too Many Requests | High | Pass | DEF-032 | Simulated DDoS successfully mitigated
TC-SEC-AUTH-004 | BR-100 | JWT Bearer Authorization auto-injection | Authenticated | Valid auth token in storage | Send API request via Axios client | Authorization: Bearer <token> header automatically attached | High | Pass |  | Original test from client
TC-SEC-SESS-001 | BR-03 | Logout clears tokens and session storage | Authenticated | Active user session with stored JWT | Click Logout button | localStorage & sessionStorage cleared | High | Pass |  | Original test from client
TC-SEC-INJ-001 | BR-60 | Stored XSS - Strips script tags from HTML input | Reader | Input field allowing HTML | Submit payload <p>Hello</p><script>alert(1)</script> | Sanitized output keeps <p>Hello</p> and strips <script> | Critical | Pass |  | Original test from client
TC-SEC-DATA-001 | BR-76 | Masks credit card numbers | Reader | Payment UI | Display saved credit card 4111222233334444 | Masked string **** **** **** 4444 rendered in UI | High | Pass |  | Original test from client

## Performance_Metrics
NFR-ID | Scenario | Tool | Target | Actual | Status | Notes
NFR-01 | Comic chapter pages must load efficiently | Manual (browser DevTools) | < 3 seconds | 1.45s | Pass | Ensures images load within acceptable limits
NFR-09 | Search results for comics must return efficiently | Manual (browser DevTools) | < 2 seconds | 272ms | Pass | Verifies basic SQL LIKE or index performance
NFR-13 | Image assets must be optimized for fast loading | Manual (browser DevTools) | Image files compressed properly | LCP = 0.46s, INP = 104ms, CLS = 0.23 | Pass | Images optimized with WebP format
NFR-18 | Static assets (images, css) must load fast | Manual (browser DevTools) | < 1.5 seconds asset load | 1.19s | Pass | Checks frontend asset optimization
NFR-19 | Reading progress syncing must not flood the database | Manual (browser DevTools) | Requests are limited/debounced on client side | Scroll triggers debounced | Pass | API requests sent at controlled intervals