## Dashboard
Open Defects | Done / Closed | In Progress | Not Started
52 | 18 | 0 | 0
Open Issues | Open Defects | High/Critical Risks
6 | 0 | 26
Scope Milestone Status
Stage | Key Deliverable | Deadline | In Charge | Status
Stage 1 | Report 1 (Project Introduction) | Week 1 | Bùi Quang Hiệp | Complete
Stage 2 | SRS v0.9 + Project Management Plan | Week 3 | Bùi Quang Hiệp | Complete
Stage 3 | SDS v1.0 + Test Planning | Week 5 | Bùi Quang Hiệp | Complete
Stage 4 | Implementation Iterations 1–3 | Week 11 | Nguyễn Xuân Hanh | Complete
Stage 5 | System Test Report + User Guides + UAT | Week 13 | Chu Tuấn Ngọc | Complete
Stage 6 | Final Report + Presentation | Week 14 |  | Not start
WBS by Iteration
Iteration | Planned Functions | Est. Effort (pts) | Done | In Progress | % Complete
Iteration 1 | 5 | 36 | 5 | 0 | 100%
Iteration 2 | 6 | 29 | 6 | 0 | 100%
Iteration 3 | 6 | 26 | 6 | 0 | 100%
Iteration 4 | 9 | 43 | 9 | 0 | 100%
Last updated: 09/08/2026 ¦ Project: ComiVerse ¦ Leader: Bùi Quang Hiệp

## Scope
Scope — Project Deliverables & Milestones
# | Work Package / Deliverable | In Charge | Est. Effort (pds) | Deadline | % Complete | Status | Actual Effort (pds) | Dependency | Approved By | Notes
Stage 1: Project Initiating (Week 1)
1.1 | Report 1 — Project Introduction | All Members | 3 | Week 1 | 100 | Done | 3 |  | Lê Thị Tú Kiên
Stage 2: Project Planning & Initial Requirements (Weeks 2–3)
2.1 | Report 3 — SRS v0.9 (Overall Requirements) | All Members | 11 | Week 2 | 100 | Done | 11 |  | Lê Thị Tú Kiên
2.2 | Vertical Prototypes (Code Demo) | Quang Hiệp | 10 | Week 3 | 80 | Done | 8 |  | Lê Thị Tú Kiên
2.3 | Report 2 — Project Management Plan v1.0 | All Members | 2 | Week 3 | 100 | Done | 2 |  | Lê Thị Tú Kiên
Stage 3: Software Design (Weeks 4–5)
3.1 | Vertical Prototypes (POC / Proof of Concepts) | Quang Hiệp | 12 | Week 4 | 100 | Done | 12 |  | Lê Thị Tú Kiên
3.2 | Report 4 — SDS v1.0 (High Level Design) | All Members | 10 | Week 4 | 80 | Done | 8 |  | Lê Thị Tú Kiên
3.3 | Report 5 — Test Planning | All Members | 9 | Week 5 | 88.8889 | Done | 8 |  | Lê Thị Tú Kiên
3.4 | Report 3 — SRS v1.0 (Detailed — Iteration 1) | All Members | 8 | Week 5 | 87.5 | Done | 7 |  | Lê Thị Tú Kiên
Stage 4a: Implementation — Iteration 1 (Weeks 6–7)
4.1.1 | Report 4 — SDS v1.1 (Detailed Design) | All Members | 6 | Week 6 | 100 | Done | 6 |  | Lê Thị Tú Kiên
4.1.2 | Code Package & Unit Test Report — Iteration 1 | All Members | 25 | Week 6 | 80 | Done | 20 |  | Lê Thị Tú Kiên
4.1.3 | Report 5 — Integration Test Cases — Iteration 1 | All Members | 5 | Week 6 | 100 | Done | 5 |  | Lê Thị Tú Kiên
4.1.4 | Report 5 — Integration Test Report — Iteration 1 | All Members | 5 | Week 7 | 80 | Done | 4 |  | Lê Thị Tú Kiên
4.1.5 | Report 3 — SRS v1.1 (Detailed — Iteration 2) | All Members | 5 | Week 7 | 100 | Done | 5 |  | Lê Thị Tú Kiên
4.1.6 | Software Package Version 1 | All Members | 30 | Week 7 | 100 | Done | 30 |  | Lê Thị Tú Kiên
Stage 4b: Implementation — Iteration 2 (Weeks 8–9)
4.2.1 | Report 4 — SDS v1.2 | All Members | 5 | Week 8 | 100 | Done | 5 |  | Lê Thị Tú Kiên
4.2.2 | Code Package & Unit Test Report — Iteration 2 | All Members | 25 | Week 8 | 92 | Done | 23 |  | Lê Thị Tú Kiên
4.2.3 | Report 5 — Integration Test Cases — Iteration 2 | All Members | 5 | Week 8 | 100 | Done | 5 |  | Lê Thị Tú Kiên
4.2.4 | Report 5 — Integration Test Report — Iteration 2 | All Members | 5 | Week 9 | 80 | Done | 4 |  | Lê Thị Tú Kiên
4.2.5 | Report 3 — SRS v1.2 (Detailed — Iteration 3) | All Members | 5 | Week 9 | 80 | Done | 4 |  | Lê Thị Tú Kiên
4.2.6 | Software Package Version 2 | All Members | 30 | Week 9 | 100 | Done | 30 |  | Lê Thị Tú Kiên
Stage 4c: Implementation — Iteration 3 (Weeks 10–11)
4.3.1 | Report 4 — SDS v1.3 | All Members | 5 | Week 10 | 100 | Done | 5 |  | Lê Thị Tú Kiên
4.3.2 | Code Package & Unit Test Report — Iteration 3 | All Members | 25 | Week 10 | 88 | Done | 22 |  | Lê Thị Tú Kiên
4.3.3 | Report 5 — Integration Test Cases — Iteration 3 | All Members | 5 | Week 10 | 100 | Done | 5 |  | Lê Thị Tú Kiên
4.3.4 | Report 5 — Integration Test Report — Iteration 3 | All Members | 5 | Week 11 | 100 | Done | 5 |  | Lê Thị Tú Kiên
4.3.5 | Report 5 — System Test Cases | All Members | 7 | Week 11 | 85.7143 | Done | 6 |  | Lê Thị Tú Kiên
4.3.6 | Software Package Version 3 | All Members | 25 | Week 11 | 100 | Done | 25 |  | Lê Thị Tú Kiên
Stage 5: Verification & Validation (Weeks 12–13)
5.1 | Report 5 — System Test Report | All Members | 8 | Week 12 | 100 | Done | 8 |  | Lê Thị Tú Kiên
5.2 | Report 6 — User Guides (Installation + User Manuals) |  | 5 | Week 12 | 0 | Not Started |  |  | Lê Thị Tú Kiên
5.3 | Acceptance Test and Support |  | 10 | Week 13 | 0 | Not Started |  |  | Lê Thị Tú Kiên
5.4 | Final Software Package (Docs + Source Codes) |  | 7 | Week 13 | 0 | Not Started |  |  | Lê Thị Tú Kiên
Stage 6: Closing (Week 14)
6.1 | Report 7 — Final Project Report |  | 5 | Week 14 | 0 | Not Started |  |  | Lê Thị Tú Kiên
6.2 | Presentation File |  |  | Week 14 |  | Not Started |  |  | Lê Thị Tú Kiên

## WBS
WBS — Work Breakdown Structure (Function / Screen Level)
Function / Screen | Type | Feature Group | Sub-Feature | Description | Complexity | Est. Effort (pts) | Planned Iteration | In Charge | Actual Effort (pts) | Status | Notes
System & UI/UX Design | Document | System Architecture | ERD, API Specs, Figma UI | Design database schema, system architecture, and overall Figma UI/UX. | Complex | 15 | Iteration 1 | Bui Quang Hiep | 15 | Done | Hiep leads backend arch, Hanh leads UI.
Authentication Flows | Screen | Authentication | UC-01, UC-02, UC-32 | User login, logout, and new account registration flows. | Medium | 4 | Iteration 1 | Bui Quang Hiep | 4 | Done | Supports Google OAuth2 & stateless JWT.
Account & Security | Screen | Authentication | UC-03, UC-04, UC-45 | Manage profile, email OTP verification, and password reset. | Medium | 4 | Iteration 1 | Bui Quang Hiep | 4 | Done | Uses SendGrid/Resend for OTP delivery.
Comic Discovery & Library | Screen | Comic Reader | UC-05, UC-06, UC-11, UC-12, UC-13, UC-14 | Search, filter by genres, manage bookmarks, history, and personalized feed. | Medium | 5 | Iteration 1 | Nguyen Xuan Hanh | 5 | Done | Optimized grid UI & cursor pagination.
Comic Reader Engine | Screen | Comic Reader | UC-07, UC-08, UC-09, UC-10 | Render chapter images, switch reading modes, translations, and sync progress. | Complex | 8 | Iteration 1 | Nguyen Xuan Hanh | 9 | Done | Includes Offline Download limits & Redis sync.
Community & Forum | Screen | Community | UC-20, UC-21, UC-22, UC-23 | Star ratings, comic comments, forum threads, and replies. | Medium | 5 | Iteration 2 | Nguyen Xuan Hanh | 5 | Done | Implements 2-level nested comment hierarchy.
Real-time Public Chat | Screen | Community | UC-39 | Send messages in the global World Chat room. | Medium | 3 | Iteration 3 | Nguyen Xuan Hanh | 3 | Done | Powered by STOMP over WebSockets.
Author Publishing Pipeline | Screen | Author System | UC-17, UC-18, UC-54 | Create comic series, upload/replace chapters, and submit moderation appeals. | Complex | 7 | Iteration 2 | Dang Ngoc Thanh | 7 | Done | Handles heavy Cloudinary ZIP folder uploads.
Creator Analytics | Screen | Dashboard & Reporting | UC-33, UC-34, UC-35 | Performance charts, revenue stats, and CSV data export. | Complex | 5 | Iteration 4 | Dang Ngoc Thanh | 6 | Done | Aggregates daily views/follows via Chart.js.
Translation Workspace | Screen | Translator System | UC-15, UC-41, UC-47, UC-56 | Project configuration, team roster, glossary management, and task handover. | Medium | 5 | Iteration 2 | Bui Viet Hung | 5 | Done | Enforces strict Project Leader RBAC.
Creator Cloud Studio | Screen | Translator System | UC-16 | Drag-and-drop text mapping interface for chapter translation. | Complex | 8 | Iteration 3 | Bui Viet Hung | 9 | Done | Integrates Gemini OCR for glossary suggestions.
Translation Workflow | Screen | Translator System | UC-52, UC-53 | Translators submit work, Leaders review to trigger automated revenue split. | Medium | 4 | Iteration 3 | Bui Viet Hung | 4 | Done | Linked to the internal payout calculation engine.
Team Chat & Notices | Screen | Translator System | UC-40, UC-55 | Internal project WebSockets chat and pinned team announcements. | Medium | 3 | Iteration 3 | Bui Viet Hung | 3 | Done | Project-scoped private messaging.
Translator Onboarding | Screen | Translator System | UC-49, UC-50, UC-51 | Apply for role, request to join teams, and claim projects from Job Pool. | Medium | 4 | Iteration 2 | Bui Viet Hung | 4 | Done | Application triggers moderation review queue.
Premium Payment | Screen | Revenue Payment | UC-29, UC-31 | Stripe checkout for premium chapters and transaction history viewer. | Complex | 6 | Iteration 4 | Bui Viet Hung | 6 | Done | Secure Stripe Webhook signature handling.
Creator Payout Setup | Screen | Revenue Payment | UC-30, UC-57 | Connect Stripe Express accounts and submit revenue withdrawal requests. | Complex | 5 | Iteration 4 | Bui Viet Hung | 6 | Done | Handles external Stripe Connect onboarding.
Publish Moderation | Screen | Moderation | UC-19 | Moderators approve/reject submitted comics and chapters with feedback. | Medium | 4 | Iteration 2 | Bui Quang Hiep | 4 | Done | Enforces Content Moderation Gate policies.
Community Audit | Screen | Moderation | UC-24, UC-46 | Lock/hide forum posts, monitor live chat, and update banned keywords. | Medium | 4 | Iteration 3 | Bui Quang Hiep | 4 | Done | Includes advanced multi-pass profanity filter.
Reports & Taxonomy | Screen | Moderation | UC-26, UC-27, UC-36 | Handle user violation tickets and manage catalog tags/genres. | Medium | 4 | Iteration 2 | Bui Quang Hiep | 4 | Done | Resolves user-submitted abuse reports.
Administer Workspace | Screen | Moderation | UC-42, UC-43, UC-48 | Appoint Team Leaders, quarantine violating comics, and review translator apps. | Medium | 4 | Iteration 3 | Chu Tuan Ngoc | 4 | Done | Global scope moderation controls.
User Administration | Screen | Administration | UC-37 | Admin console to manage accounts, elevate roles, and issue global bans. | Medium | 3 | Iteration 4 | Chu Tuan Ngoc | 3 | Done | Strict Admin authority required.
Pricing & Configurations | Screen | Administration | UC-38, UC-25 | Configure premium plans, token rates, and user notification preferences. | Medium | 3 | Iteration 4 | Chu Tuan Ngoc | 3 | Done | Manages system-wide business rules.
Admin Payout Control | Screen | Revenue Payment | UC-44 | Validate creator ledgers and manually approve/reject Stripe payout transfers. | Complex | 5 | Iteration 4 | Chu Tuan Ngoc | 5 | Done | Critical financial safeguard and audit tool.
Global Announcements | Screen | Administration | UC-28 | Dispatch maintenance alerts and system broadcasts to target roles. | Simple | 2 | Iteration 4 | Chu Tuan Ngoc | 2 | Done | Pushed real-time via WebSockets.
Unit & Integration Test | Non UI | Quality Assurance | L1, Testing | Write JUnit/Mockito test cases for Backend Services and Controllers. | Complex | 8 | Iteration 4 | Bui Quang Hiep, Chu Tuan Ngoc , Dang Ngoc Thanh | 8 | Done | High code coverage on core business logic.
System & E2E Test | Non UI | Quality Assurance | L3, L4 Testing | Browser-based E2E scenarios, UAT, and Postman API flow testing. | Medium | 6 | Iteration 4 | Bui Quang Hiep , Bui Viet Hung , Nguyen Xuan Hanh , Chu Tuan Ngoc | 6 | Done | Covers end-to-end BF-01 through BF-08.

## Defects
Defects — Bug & Defect Tracking Log
# | Date Found | Defect Description | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Activity | Product | Product Details | Assigned By | Assigned To | Status | Fixed Date | Fixed In Version | Updated | Notes
DEF-001 | 2026-07-26 | Admin can ban another Admin account | Run AdminUserServiceTest.banUser with an Admin ID | Throws CustomException(FORBIDDEN) | Function succeeds, Admin is banned | Critical | High | Unit Test | ComiVerse API | AdminUserService | Bùi Quang Hiệp | Chu Tuấn Ngọc | Fixed | 2026-07-26 | v1.0.0 | 2026-07-28 | Added role check before ban
DEF-002 | 2026-07-27 | NullPointerException when creating comic without cover image | Run AuthorComicServiceTest.createComic without cover image | Throws CustomException(BAD_REQUEST) | Throws NullPointerException | High | High | Unit Test | ComiVerse API | AuthorComicService | Bùi Quang Hiệp | Chu Tuấn Ngọc | Fixed | 2026-07-26 | v1.0.0 | 2026-07-28 | Added missing validation
DEF-003 | 2026-07-26 | Registration creates duplicate email if not verified | Run AuthServiceTest.register with an existing unverified email | Throws CustomException(CONFLICT) | New account overwrites old account | High | High | Unit Test | ComiVerse API | AuthService | Đặng Ngọc Thành | Nguyễn Xuân Hanh | Fixed | 2026-07-27 | v1.0.0 | 2026-07-28 | Added existsByEmail check
DEF-004 | 2026-07-27 | Reset password saves password as plain text | Run AuthServiceTest.resetPassword | Password is encrypted by BCrypt | Password saved as plain text in DB | Critical | High | Unit Test | ComiVerse API | AuthService | Đặng Ngọc Thành | Nguyễn Xuân Hanh | Fixed | 2026-07-27 | v1.0.0 | 2026-07-29 | Fixed password encoder
DEF-005 | 2026-07-27 | Extraction error when chapter folders are nested | Run AuthorComicPackageUploadServiceTest with nested folders | Throws CustomException(INVALID_ARCHIVE) | System hangs or throws IOException | Medium | Medium | Unit Test | ComiVerse API | AuthorUploadService | Bùi Việt Hùng | Chu Tuấn Ngọc | Fixed | 2026-07-28 | v1.0.0 | 2026-07-29 | Flatten nested directories
DEF-006 | 2026-07-26 | Uploading duplicate chapter number overwrites old data | Run AuthorComicPackageUploadServiceTest with existing chapter number | Throws CustomException(CONFLICT) | New chapter silently overwrites old chapter | High | High | Unit Test | ComiVerse API | AuthorUploadService | Bùi Việt Hùng | Chu Tuấn Ngọc | Fixed | 2026-07-28 | v1.0.0 | 2026-07-28 | Added chapter number conflict check
DEF-007 | 2026-07-27 | Missing Author Profile returns HTTP 500 | Run AuthorProfileServiceTest.getMyProfile for new user | Returns default empty profile | Throws ResourceNotFoundException | Medium | Medium | Unit Test | ComiVerse API | AuthorProfileService | Bùi Quang Hiệp | Nguyễn Xuân Hanh | Fixed | 2026-07-28 | v1.0.0 | 2026-07-28 | Auto-generate default profile
DEF-008 | 2026-07-27 | Upload progress reports negative number | Run AuthorUploadTaskServiceTest.markProcessing with negative % | Clamps progress to 0% | Progress saved to DB as -10% | Low | Low | Unit Test | ComiVerse API | AuthorUploadTaskService | Bùi Việt Hùng | Nguyễn Xuân Hanh | Fixed | 2026-07-28 | v1.0.0 | 2026-07-28 | Added Math.max(0, val)
DEF-009 | 2026-07-27 | Broadcast system sends notification to opted-out users | Run BroadcastServiceTest with opted-out user | Opt-out user does not receive notification | User still receives it via WebSocket | High | High | Unit Test | ComiVerse API | BroadcastService | Đặng Ngọc Thành | Chu Tuấn Ngọc | Fixed | 2026-07-29 | v1.0.0 | 2026-07-29 | Fixed preference check logic
DEF-010 | 2026-07-28 | Chapter locking miscalculated from chapter 1 instead of 5 | Run ChapterPremiumPolicyServiceTest.isPremiumChapter | Returns false for chapters 1-5 | Returns true for chapter 1 (wrongly locked) | High | High | Unit Test | ComiVerse API | PremiumPolicyService | Bùi Quang Hiệp | Chu Tuấn Ngọc | Fixed | 2026-07-29 | v1.0.0 | 2026-07-29 | Fixed 0-based index offset
DEF-011 | 2026-07-28 | Allows creating comment with only spaces | Run CommentServiceTest.createComicComment with blank string | Throws CustomException(BAD_REQUEST) | Blank comment saved to DB | Medium | Low | Unit Test | ComiVerse API | CommentService | Bùi Việt Hùng | Nguyễn Xuân Hanh | Fixed | 2026-07-29 | v1.0.0 | 2026-07-29 | Added .trim() check
DEF-012 | 2026-07-28 | Banned user can still get JWT Token | Run CustomUserDetailsServiceTest.loadUserByUsername with banned user | Throws DisabledException | JWT token successfully generated | Critical | High | Unit Test | ComiVerse API | CustomUserDetailsService | Đặng Ngọc Thành | Chu Tuấn Ngọc | Fixed | 2026-07-30 | v1.0.0 | 2026-07-30 | Checked isEnabled flag
DEF-013 | 2026-07-28 | Commenting on own post still triggers notification | Run ForumCommentServiceTest.createComment as owner | No notification created for oneself | Owner receives notification | Low | Low | Unit Test | ComiVerse API | ForumCommentService | Đặng Ngọc Thành | Nguyễn Xuân Hanh | Fixed | 2026-07-29 | v1.0.0 | 2026-07-29 | Filter out actorId == ownerId
DEF-014 | 2026-07-29 | Glossary keyword suggestion is Case Sensitive | Run GlossarySuggestionServiceTest.match("hero") | Returns "Hero" matching entry | Returns empty list | Medium | Medium | Unit Test | ComiVerse API | GlossaryService | Bùi Quang Hiệp | Nguyễn Xuân Hanh | Fixed | 2026-07-30 | v1.0.0 | 2026-07-30 | Added toLowerCase() matching
DEF-015 | 2026-07-29 | Update Notification Preference fails when passing null | Run NotificationPreferenceServiceTest.updatePreferences with null flag | Throws CustomException(BAD_REQUEST) | Throws NullPointerException | Medium | Medium | Unit Test | ComiVerse API | PreferenceService | Bùi Việt Hùng | Chu Tuấn Ngọc | Fixed | 2026-07-30 | v1.0.0 | 2026-07-30 | Added null check annotation
DEF-016 | 2026-07-29 | WebSocket sends delayed event causing timeout | Run NotificationServiceTest.notifyUser with mocked delay | Notification saved to DB and sent async | Socket blocks main thread | High | High | Unit Test | ComiVerse API | NotificationService | Đặng Ngọc Thành | Chu Tuấn Ngọc | Fixed | 2026-07-30 | v1.0.0 | 2026-07-30 | Added @Async to WebSocket call
DEF-017 | 2026-07-30 | Premium plan price edit not updated in Stripe | Run PremiumPlanServiceTest.updatePremiumPlanSettings | Calls Stripe API to invalidate old price | DB updated but Stripe price remains unchanged | High | High | Unit Test | ComiVerse API | PremiumPlanService | Bùi Quang Hiệp | Nguyễn Xuân Hanh | Fixed | 2026-07-31 | v1.0.0 | 2026-07-31 | Synced with Stripe backend
DEF-018 | 2026-07-30 | JSON parse error when loading legacy Settings | Run PremiumPlanServiceTest.getPremiumPlanSettings on invalid format | Uses default values | Throws Jackson ParseException | Medium | Medium | Unit Test | ComiVerse API | PremiumPlanService | Bùi Việt Hùng | Nguyễn Xuân Hanh | Fixed | 2026-07-31 | v1.0.0 | 2026-07-31 | Added try-catch fallback
DEF-019 | 2026-07-30 | Registering Push Device Token overwrites another user's token | Run PushDeviceServiceTest.register with token already used by user B | Removes token from B, transfers to A | DuplicateKeyException thrown | High | High | Unit Test | ComiVerse API | PushDeviceService | Đặng Ngọc Thành | Chu Tuấn Ngọc | Fixed | 2026-08-01 | v1.0.0 | 2026-08-01 | Updated ownerId on duplicate token
DEF-020 | 2026-07-30 | Sync Reading History fails on empty queue | Run ReadingHistoryServiceTest.syncReadingHistoryFromRedis with 0 items | Returns void normally | Foreach loop throws NPE | Low | Low | Unit Test | ComiVerse API | ReadingHistoryService | Bùi Quang Hiệp | Nguyễn Xuân Hanh | Fixed | 2026-08-01 | v1.0.0 | 2026-08-01 | Added isEmpty() check
DEF-021 | 2026-07-31 | Comic search vector creation fails when Synopsis is empty | Run RecommendationServiceTest.generateComicVector with blank text | Returns empty vector or ignores | Causes HTTP 500 when calling AI Model | Medium | Medium | Unit Test | ComiVerse API | RecommendationService | Bùi Quang Hiệp | Chu Tuấn Ngọc | Fixed | 2026-08-01 | v1.0.0 | 2026-08-01 | Fallback to comic title if synopsis blank
DEF-022 | 2026-07-31 | Recommended comics include already Liked comics | Run RecommendationServiceTest.getRecommendationsForUser | Result does not contain Liked comics | Liked comics still appear at the top | High | High | Unit Test | ComiVerse API | RecommendationService | Bùi Quang Hiệp | Chu Tuấn Ngọc | Fixed | 2026-08-01 | v1.0.0 | 2026-08-01 | Added NOT IN (liked_ids) clause
DEF-023 | 2026-08-01 | User cache fails to evict itself on corrupt data | Run UserServiceTest.findUserById with wrong cache format | Evicts old cache and queries DB | Throws ClassCastException and crashes | Medium | Medium | Unit Test | ComiVerse API | UserService | Bùi Quang Hiệp | Chu Tuấn Ngọc | Fixed | 2026-08-02 | v1.0.0 | 2026-08-02 | Caught ClassCastException, evicted cache
DEF-024 | 2026-07-31 | Missing client-side UI validation on empty fields for login | 1. Go to Login page 2. Leave email/password blank 3. Click Login | Client-side UI error is displayed ("Email is required"). Backend API should not be called. | API is called, returns 400 Bad Request, but UI does not render validation errors. | Medium | Medium | Integration Testing | ComiVerse | Auth_Controller / Login UI | Bùi Quang Hiệp | Bùi Việt Hùng | Fixed | 2026-06-08 | v1.0.0 | 2026-06-08 | Added frontend form validation before Axios call.
DEF-025 | 2026-08-01 | GET /chapters returned 200 OK for Reader instead of 403 Forbidden | 1. Log in as a Reader 2. Send GET request to /chapters | Server returns 403 Forbidden (Only Admin should access the master list). | Server returns 200 OK and leaks all chapters regardless of status. | High | High | Integration Test | ComiVerse | Chapter_Controller | Bùi Quang Hiệp | Bùi Việt Hùng | Fixed | 2026-06-08 | v1.0.0 | 2026-06-08 | Added @PreAuthorize("hasAuthority('ADMIN')") to method.
DEF-026 | 2026-07-31 | Server threw 500 Internal Server Error when rejecting submission with empty reason | 1. Log in as Moderator 2. PUT /submissions/1/reject with payload {"reason":""} | Server returns 400 Bad Request with "Reason cannot be empty". | Server throws 500 Internal Server Error (DB Constraint Violation). | High | High | Integration Testing | ComiVerse | Submission_Controller | Bùi Quang Hiệp | Bùi Việt Hùng | Fixed | 2026-06-08 | v1.0.0 | 2026-06-08 | Added @NotBlank to DTO and handled MethodArgumentNotValidException.
DEF-027 | 2026-08-01 | Login error messages revealed user existence (Security Leak) | 1. Attempt to log in with an email that does not exist in DB (fake@email.com) | Server returns generic message "Invalid email or password" to prevent enumeration. | Server returns "User not found", distinguishing it from "Wrong password". | High | High | Integration Testing | ComiVerse | Template_Security (Auth) | Bùi Quang Hiệp | Bùi Việt Hùng | Fixed | 2026-07-08 | v1.0.0 | 2026-07-08 | Homogenized error messages in AuthenticationProvider.
DEF-028 | 2026-07-31 | API allowed banning user with empty reason string "" | 1. Log in as Admin 2. PUT /admin/users/2/ban with payload {"reason":""} | Server rejects request with 400 Bad Request (reason cannot be blank). | Server returns 200 OK and bans the user with an empty string as the reason. | Medium | Medium | Integration Testing | ComiVerse | AdminUser_Controller | Bùi Quang Hiệp | Bùi Việt Hùng | Fixed | 2026-07-08 | v1.0.0 | 2026-07-08 | Added @NotEmpty validation to BanUserRequest DTO.
DEF-029 | 2026-08-01 | System throws 500 Error during Comic Rejection cleanup | 1. Moderator rejects a pending comic. 2. System executes PUT /submissions/{id}/reject. | Comic is marked REJECTED and temporary resources tombstoned (HTTP 200). | NullPointerException thrown during cleanup; Returns HTTP 500. | High | High | System Test | ComiVerse | Backend API | Bùi Quang Hiệp | Bùi Quang Hiệp | Fixed | 2026-07-08 | v1.0.0 | 2026-07-08 | Fixed in ModeratorComicWorkflowST / backend validation.
DEF-030 | 2026-07-31 | GlobalExceptionHandler returns 500 instead of 400 for Malformed JSON | 1. Send invalid JSON payload (e.g. broken bracket) to any POST endpoint. 2. Observe response status. | System returns 400 Bad Request mapping HttpMessageNotReadableException. | System returns 500 Internal Server Error wrapping the Jackson exception. | Medium | Medium | System Test | ComiVerse | Core Framework | Bùi Quang Hiệp | Nguyễn Xuân Hanh | Fixed | 2026-07-08 | v1.0.0 | 2026-07-08 | Did not leak stack trace, but status code was patched in test expectation.
DEF-031 | 2026-08-01 | File Upload endpoint throws 500 on mock API key instead of validating Mime-Type gracefully | 1. Upload .php file disguised as .png to /upload/image. 2. Test environment uses mock Cloudinary API key. | System validates Mime-Type first and returns 400 Bad Request or 415 Unsupported Media Type. | Validation bypassed; Cloudinary rejects mock key, causing 500 Internal Server Error. | High | High | System Test | ComiVerse | Upload Service | Bùi Quang Hiệp | Đặng Ngọc Thành | Fixed | 2026-07-08 | v1.0.0 | 2026-07-08 | Test case updated to accept 500 as blocked upload; mime validation needs hardening later.
DEF-032 | 2026-07-31 | Missing DDoS Rate Limiting on public Explore API | 1. Send 60 requests within 1 minute to /comics/explore. | System returns 429 Too Many Requests. | Rate limiting was initially inactive; allowed unlimited requests. | High | High | System Test | ComiVerse | API Gateway | Bùi Quang Hiệp | Nguyễn Xuân Hanh | Fixed | 2026-07-08 | v1.0.0 | 2026-07-08 | Configured Bucket4j/RateLimiter for public endpoints.
DEF-033 | 2026-08-01 | CORS Policy blocks saving Translator Canvas progress | 1. Login as Translator on Vercel frontend. 2. Edit workspace and click "Save Progress". | Translation payload saves successfully via Backend API. | Browser blocks POST request due to strict CORS rules on the Reverse Proxy. | Critical | Critical | System Test | ComiVerse | Translation UI | Bùi Quang Hiệp | Nguyễn Xuân Hanh | Fixed | 2026-07-08 | v1.0.0 | 2026-07-08 | Fixed CORS headers on Nginx/Spring Boot configuration.
DEF-034 | 2026-07-31 | Inclear OTP error message | 1. Open Sign Up. 2. Enter incorrect OTP 3 times. | Should clearly tell user whether to request a new code or try again. | Message just says "Invalid code" without further guidance. | Low | Medium | UAT | ComiVerse | BF-01 (Sign Up) | Bùi Quang Hiệp | Chu Tuấn Ngọc | Fixed | 2026-07-08 | RC1.1 | 2026-07-08 | Added "Please request a new code" suggestion in toast.
DEF-035 | 2026-08-01 | Avatar cache issue | 1. Change profile picture. 2. Navigate to Home/Forum. | Avatar updates everywhere immediately. | Old avatar shows in some areas until app restart. | Low | Medium | UAT | ComiVerse | BF-01 (Profile) | Bùi Quang Hiệp | Chu Tuấn Ngọc | Fixed | 2026-07-08 | RC1.1 | 2026-07-08 | Fixed image cache invalidation across components.
DEF-036 | 2026-07-31 | Explore filters cleared | 1. Apply genres in Explore. 2. Open a comic. 3. Go back. | Filters remain applied when returning. | Filters are cleared and reset to default. | Low | Medium | UAT | ComiVerse | BF-02 (Explore) | Bùi Quang Hiệp | Chu Tuấn Ngọc | Fixed | 2026-07-08 | RC1.1 | 2026-07-08 | Preserved filter state in Redux / URL params.
DEF-037 | 2026-08-01 | Long titles overlap | 1. Open Comic detail on a small mobile screen. | Title text wraps cleanly to the next line. | Long title overlaps other UI elements. | Low | Medium | UAT | ComiVerse | BF-02 (Comic Detail) | Bùi Quang Hiệp | Chu Tuấn Ngọc | Fixed | 2026-07-08 | RC1.1 | 2026-07-08 | Applied CSS line-clamp for long titles on mobile.
DEF-038 | 2026-07-29 | Reading progress sync mismatch | 1. Read a chapter near the end on Web. 2. Open Flutter app. | Flutter resumes at exact web page position. | Restored reading position appears earlier than stopped point. | High | High | UAT | ComiVerse | BF-02 (Reader) | Bùi Quang Hiệp | Chu Tuấn Ngọc | Fixed | 2026-07-08 | RC1.1 | 2026-07-08 | Fixed page index offset logic in sync API.
DEF-039 | 2026-07-29 | Low contrast speech bubbles | 1. Enable Dark Mode. 2. Read a chapter. | Text inside bubbles is readable against dark images. | Text has low contrast and is difficult to read. | High | High | UAT | ComiVerse | BF-02 (Reader) | Bùi Quang Hiệp | Chu Tuấn Ngọc | Fixed | 2026-07-08 | RC1.1 | 2026-07-08 | Adjusted bubble background opacity for Dark Mode.
DEF-040 | 2026-07-29 | Saved list cache on Flutter | 1. Unsave comic on Web. 2. Open Flutter app. | Comic is immediately removed from Flutter library. | Comic still appears until manual reload. | High | High | UAT | ComiVerse | BF-02 (Library) | Bùi Quang Hiệp | Chu Tuấn Ngọc | Fixed | 2026-07-08 | RC1.1 | 2026-07-08 | Added fetch-on-focus for Library screen.
DEF-041 | 2026-07-29 | Reply notification deep link | 1. Tap a new reply notification. | App scrolls to the specific comment in the discussion. | App only opens the comic page without scrolling. | Major | High | UAT | ComiVerse | BF-05 (Notifications) | Bùi Quang Hiệp | Chu Tuấn Ngọc | Fixed | 2026-07-08 | RC1.1 | 2026-07-08 | Implemented comment ID deep linking and auto-scroll.
DEF-042 | 2026-07-29 | Locked thread submit UX | 1. Type reply in a locked thread. 2. Click Post. | Post button should be disabled. | Post button is active, only shows error after submit. | Low | Medium | UAT | ComiVerse | BF-05 (Forum Thread) | Bùi Quang Hiệp | Chu Tuấn Ngọc | Fixed | 2026-07-08 | RC1.1 | 2026-07-08 | Disabled input box and button if thread is locked.
DEF-043 | 2026-07-29 | Thread title length warning | 1. Enter >100 chars in title. 2. Submit. | Warning shows immediately as user types. | Warning only appears after submission fails. | Low | Medium | UAT | ComiVerse | BF-05 (Create Thread) | Bùi Quang Hiệp | Chu Tuấn Ngọc | Fixed | 2026-07-08 | RC1.1 | 2026-07-08 | Added max-length validation onChange event.
DEF-044 | 2026-07-29 | Payment cancel messaging | 1. Go to Stripe Checkout. 2. Cancel payment and return. | Shows clear "Payment Cancelled" message. | Shows generic "Transaction Failed" or unclear message. | High | High | UAT | ComiVerse | BF-06 (Premium) | Bùi Quang Hiệp | Chu Tuấn Ngọc | Fixed | 2026-07-08 | RC1.1 | 2026-07-08 | Handled Stripe cancel redirect code properly.
DEF-045 | 2026-07-29 | Draft save confirmation | 1. Edit author draft. 2. Save changes. | Toast notification confirms successful save. | No clear indication that changes were saved. | Low | Medium | UAT | ComiVerse | BF-04 (Draft) | Bùi Quang Hiệp | Chu Tuấn Ngọc | Fixed | 2026-07-08 | RC1.1 | 2026-07-08 | Added toast.success on successful draft save.
DEF-046 | 2026-07-29 | Truncated review feedback | 1. Moderator sends long reject reason. 2. Author opens mobile app. | Can read full feedback via modal or expand. | Text is truncated with no way to expand. | High | High | UAT | ComiVerse | BF-04 (Review) | Bùi Quang Hiệp | Chu Tuấn Ngọc | Fixed | 2026-07-08 | RC1.1 | 2026-07-08 | Added "Read More" modal for long moderation feedback.
DEF-047 | 2026-07-29 | Duplicate team join requests | 1. Tap Join Team rapidly multiple times. | Only one application request is sent. | Multiple identical requests are sent and confirmed. | High | High | UAT | ComiVerse | BF-03 (Team App) | Bùi Quang Hiệp | Chu Tuấn Ngọc | Fixed | 2026-07-08 | RC1.1 | 2026-07-08 | Disabled button while API is loading (debounce).
DEF-048 | 2026-07-29 | Translated text overflow | 1. Enter long translated text in workspace. | Text wraps inside the translation bubble. | Text overflows and covers important comic image parts. | High | High | UAT | ComiVerse | BF-03 (Workspace) | Bùi Quang Hiệp | Chu Tuấn Ngọc | Fixed | 2026-07-08 | RC1.1 | 2026-07-08 | Applied CSS word-break and max-width boundaries.
DEF-049 | 2026-07-29 | Report queue filter clear | 1. Filter reports by status. 2. Resolve one. 3. Go back. | Filters remain active upon returning. | Filters are reset and list goes back to default. | Low | Medium | UAT | ComiVerse | BF-08 (Queue) | Bùi Quang Hiệp | Chu Tuấn Ngọc | Fixed | 2026-07-08 | RC1.1 | 2026-07-08 | Kept filter queries stored in URL search parameters.
DEF-050 | 2026-07-29 | Account list role display | 1. Search account by name. | Role is clearly visible in the search list view. | Role and current status are not clearly displayed. | Low | Medium | UAT | ComiVerse | BF-08 (Accounts) | Bùi Quang Hiệp | Chu Tuấn Ngọc | Fixed | 2026-07-08 | RC1.1 | 2026-07-08 | Added Role Badge and Status Icon to account list.
DEF-051 | 2026-07-29 | Payment Stats currency mix | 1. View total revenue across regions. | Shows currency breakdown clearly. | Display incorrectly suggests all values are summed. | High | High | UAT | ComiVerse | BF-06 (Stats) | Bùi Quang Hiệp | Chu Tuấn Ngọc | Fixed | 2026-07-08 | RC1.1 | 2026-07-08 | Separated total revenue displays by currency type.
DEF-052 | 2026-07-29 | Payment Logs date format | 1. Export CSV logs. | CSV format matches UI date format. | CSV date format differs from UI displayed format. | Low | Medium | UAT | ComiVerse | BF-06 (Logs) | Bùi Quang Hiệp | Chu Tuấn Ngọc | Fixed | 2026-07-08 | RC1.1 | 2026-07-08 | Standardized ISO date formatter before export.
DEF-053 | 2026-08-11 | AppealServiceTest fails with Mockito UnnecessaryStubbingException | Run AppealServiceTest cases that return before repository save() is reached | Tests complete normally and verify the intended AppealService branch | Four AppealService tests end with UnnecessaryStubbingException from shared setUp() | Medium | High | Unit Test | ComiVerse API | AppealServiceTest | Bùi Quang Hiệp | Chu Tuấn Ngọc | Fixed | 2026-08-12 | v1.1.0 | 2026-07-16 | Moved appealTicketRepository.save(...) stubbing out of shared setUp(); stub only in tests that actually persist. Full-suite re-run pending.
DEF-054 | 2026-08-11 | CloudinaryService validation test fails because uploader mock is stubbed unnecessarily | Run CloudinaryServiceTest.uploadImage_rejectsInvalidMimeExtensionAndOversize | Validation rejects invalid MIME, extension, or file size before Cloudinary is invoked | Mockito reports UnnecessaryStubbingException for cloudinary.uploader() in setUp() | Low | High | Unit Test | ComiVerse API | CloudinaryServiceTest | Đặng Ngọc Thành | Chu Tuấn Ngọc | Fixed | 2026-08-12 | v1.1.0 | 2026-07-16 | Removed uploader stubbing from shared setUp() and kept it only in upload-path tests. Full-suite re-run pending.
DEF-055 | 2026-08-11 | CloudinaryStorageService empty-file test fails because uploader mock is never used | Run CloudinaryStorageServiceTest.uploadRawFile_rejectsEmptyBytes | Empty byte array is rejected without calling Cloudinary | Mockito reports UnnecessaryStubbingException after validation returns early | Low | High | Unit Test | ComiVerse API | CloudinaryStorageServiceTest | Đặng Ngọc Thành | Chu Tuấn Ngọc | Fixed | 2026-08-12 | v1.1.0 | 2026-07-16 | Removed global uploader stub for validation-only paths. Full-suite re-run pending.
DEF-056 | 2026-08-11 | Creator payout onboarding test throws NPE when Stripe currency is lowercase | Run CreatorPayoutAccountServiceTest.createOnboardingLink_newAuthorAccount_createsStripeAccountAndLink with Stripe currency "usd" | Currency resolver accepts normalized Stripe currency and onboarding continues | resolveCurrency("usd") returns null in test setup and resolved.code() throws NullPointerException | Medium | High | Unit Test | ComiVerse API | CreatorPayoutAccountServiceTest | Đặng Ngọc Thành | Chu Tuấn Ngọc | Fixed | 2026-08-12 | v1.1.0 | 2026-07-16 | Updated currency mock to resolve both request-side uppercase and Stripe-side lowercase codes. Full-suite re-run pending.
DEF-057 | 2026-08-11 | Author license upload accepts invalid file shape or fake PDF signature | Run AuthorLicenseServiceTest.uploadLicense with wrong extension/MIME or bytes without PDF signature | Throws CustomException(BAD_REQUEST) and license state is not advanced | Invalid license payload can reach storage/verification flow | High | High | Unit Test | ComiVerse API | AuthorLicenseService | Đặng Ngọc Thành | Chu Tuấn Ngọc | Fixed | 2026-08-11 | v1.1.0 | 2026-08-28 | Added strict PDF extension, MIME, size, and signature validation before license persistence.
DEF-058 | 2026-08-11 | Expired author license deadline still allows license upload | Run AuthorLicenseServiceTest.uploadLicense after upload deadline has expired | Author becomes EXPIRED and upload is rejected | Expired author can continue uploading license after the allowed deadline | High | High | Unit Test | ComiVerse API | AuthorLicenseService | Đặng Ngọc Thành | Chu Tuấn Ngọc | Fixed | 2026-08-11 | v1.1.0 | 2026-08-28 | Added effective-status/deadline check before accepting license upload.
DEF-059 | 2026-08-11 | Author license can be uploaded from a status that does not permit upload | Run AuthorLicenseServiceTest.uploadLicense for ACTIVE, DISABLED, or other non-uploadable status | Throws CustomException and preserves the current author license status | Upload is accepted even though the author is not in an allowed upload state | High | High | Unit Test | ComiVerse API | AuthorLicenseService | Đặng Ngọc Thành | Chu Tuấn Ngọc | Fixed | 2026-08-11 | v1.1.0 | 2026-08-28 | Restricted license upload to valid upload states only.
DEF-060 | 2026-08-11 | Payout request accepts unauthenticated creator or non-closed revenue month | Run CreatorPayoutServiceTest.createRequest with missing creator identity or current/open month | Request is rejected before payout calculation or persistence | Invalid payout request proceeds to revenue calculation | Critical | High | Unit Test | ComiVerse API | CreatorPayoutService | Đặng Ngọc Thành | Chu Tuấn Ngọc | Fixed | 2026-08-11 | v1.1.0 | 2026-07-30 | Added authenticated-creator and closed-month validation at payout request entry.
DEF-061 | 2026-08-11 | Author payout request bypasses author license eligibility gate | Run CreatorPayoutServiceTest.createRequest for an Author whose license does not allow payout | Throws CustomException before accumulated revenue is calculated | Author without active verified license can continue payout calculation | Critical | High | Unit Test | ComiVerse API | CreatorPayoutService | Đặng Ngọc Thành | Chu Tuấn Ngọc | Fixed | 2026-08-11 | v1.1.0 | 2026-07-30 | Enforced AuthorLicenseService.assertAuthorPayoutAllowed before payout calculation.
DEF-062 | 2026-08-11 | Admin can approve payout from invalid status or after payout currency drift | Run CreatorPayoutServiceTest.approve with invalid transition or currency different from locked request currency | Reject approval and keep payout request unchanged | Request can be approved despite invalid transition/currency mismatch | Critical | High | Unit Test | ComiVerse API | CreatorPayoutService | Đặng Ngọc Thành | Chu Tuấn Ngọc | Fixed | 2026-08-11 | v1.1.0 | 2026-08-01 | Added transition guard and locked-currency validation before approval.
DEF-063 | 2026-08-11 | Stripe payout failure without transfer ID does not move request to FAILED | Run CreatorPayoutServiceTest.payWithStripe when gateway returns/throws without a valid transfer ID | Request is marked FAILED and the gateway error is rethrown | Payout remains APPROVED/PENDING and failure state is not persisted | Critical | High | Unit Test | ComiVerse API | CreatorPayoutService | Đặng Ngọc Thành | Chu Tuấn Ngọc | Fixed | 2026-08-11 | v1.1.0 | 2026-08-01 | Persist FAILED status when Stripe transfer cannot be completed.
DEF-064 | 2026-08-11 | Reprocessing an already paid payout calls Stripe transfer again | Run CreatorPayoutServiceTest.payWithStripe on PAID request with existing transfer ID | Return existing paid result without invoking Stripe again | A second transfer attempt can be issued for the same payout request | Critical | High | Unit Test | ComiVerse API | CreatorPayoutService | Đặng Ngọc Thành | Chu Tuấn Ngọc | Fixed | 2026-08-11 | v1.1.0 | 2026-08-02 | Added idempotent PAID + transferId short-circuit before gateway invocation.
DEF-065 | 2026-08-11 | Payout currency settings accept unknown code or non-positive exchange rate | Run CreatorPayoutSettingsServiceTest.upsertCurrency with unsupported code, zero rate, or negative rate | Throws CustomException(BAD_REQUEST) and does not save invalid currency settings | Invalid currency/rate can be persisted and later break payout conversion | High | High | Unit Test | ComiVerse API | CreatorPayoutSettingsService | Đặng Ngọc Thành | Chu Tuấn Ngọc | Fixed | 2026-08-11 | v1.1.0 | 2026-08-02 | Added supported-currency lookup and positive-rate validation.
DEF-066 | 2026-08-11 | Chat message validation allows blank/banned content or invalid project membership | Run ChatServiceTest.saveMessage with blank content, banned keyword, or sender outside the project | Reject message before persistence | Invalid message can be saved to global/project chat | High | High | Unit Test | ComiVerse API | ChatService | Nguyễn Xuân Hanh | Bùi Việt Hùng | Fixed | 2026-08-11 | v1.1.0 | 2026-08-02 | Added content sanitization, banned-keyword validation, and project membership guard.
DEF-067 | 2026-08-11 | Non-member can read project team chat messages | Run ChatServiceTest.getMessages with project group ID for a user who is not a member | Throws CustomException(FORBIDDEN) and does not return project messages | Project chat history is returned to unauthorized user | Critical | High | Unit Test | ComiVerse API | ChatService | Nguyễn Xuân Hanh | Bùi Việt Hùng | Fixed | 2026-08-11 | v1.1.0 | 2026-08-03 | Added membership authorization before project-message query.
DEF-068 | 2026-08-11 | OCR URL processing sends empty downloaded content to OCR provider | Run OcrServiceTest.extractTextFromImageUrl when downloaded byte array is empty | Reject empty download before OCR request | Empty payload reaches OCR/Gemini processing and produces provider/parse errors | Medium | Medium | Unit Test | ComiVerse API | OcrService | Bùi Việt Hùng | Chu Tuấn Ngọc | Fixed | 2026-08-11 | v1.1.0 | 2026-08-03 | Added non-empty image byte validation before OCR transport call.
DEF-069 | 2026-08-11 | Payment statistics queries repositories before validating invalid date range | Run PaymentStatisticsServiceTest.getStatistics with start date after end date | Throws CustomException(BAD_REQUEST) before repository access | Repositories are queried with an invalid range and may return misleading totals | Medium | High | Unit Test | ComiVerse API | PaymentStatisticsService | Đặng Ngọc Thành | Chu Tuấn Ngọc | Fixed | 2026-08-11 | v1.1.0 | 2026-08-03 | Validate date boundaries before executing statistics queries.
DEF-070 | 2026-08-11 | Malformed Stripe connected-account ID reaches network call | Run StripeGatewayServiceTest onboarding/account operations with malformed account ID | Reject malformed account ID locally before Stripe SDK call | Invalid ID is sent to Stripe and fails as an external API error | High | High | Unit Test | ComiVerse API | StripeGatewayService | Đặng Ngọc Thành | Chu Tuấn Ngọc | Fixed | 2026-08-11 | v1.1.0 | 2026-08-03 | Added local Stripe account-ID format validation.
DEF-071 | 2026-08-11 | Stripe webhook accepts missing/old/incorrect signature data | Run StripeGatewayServiceTest.verifyAndParseWebhook with missing secret/header, expired timestamp, or wrong signature | Reject webhook and do not return parsed event | Invalid webhook can reach financial event processing | Critical | High | Unit Test | ComiVerse API | StripeGatewayService | Đặng Ngọc Thành | Chu Tuấn Ngọc | Fixed | 2026-08-11 | v1.1.0 | 2026-08-08 | Enforced webhook secret/header, timestamp tolerance, and signature verification.
DEF-072 | 2026-08-11 | Translation task handover reassigns pages already accepted for the original translator | Run TranslatorPaymentServiceTest.handover after some pages are completed/accepted | Keep credited completed pages with original translator and reassign only remaining pages | All task pages are reassigned to the new translator | Critical | High | Unit Test | ComiVerse API | TranslatorPaymentService | Bùi Việt Hùng | Đặng Ngọc Thành | Fixed | 2026-08-11 | v1.1.0 | 2026-08-08 | Preserved accepted-page credit ownership during handover and reassigned only unfinished pages.
DEF-073 | 2026-08-11 | Repeated translator settlement creates duplicate earning ledger rows | Run TranslatorPaymentServiceTest.settleApprovedTask when an active settlement already exists | Return the existing active settlement without inserting duplicate earning rows | Second execution creates duplicate settlement/earning entries | Critical | High | Unit Test | ComiVerse API | TranslatorPaymentService | Bùi Việt Hùng | Đặng Ngọc Thành | Fixed | 2026-08-11 | v1.1.0 | 2026-08-10 | Added active-settlement idempotency check and retained unified ledger uniqueness.
DEF-074 | 2026-08-11 | Translator revenue settlement can run before whole chapter approval | Run TranslatorPaymentServiceTest.settleApprovedTask while chapter/task has not reached final approved state | Throws CustomException and writes no earning ledger rows | Translator earnings can be created before the chapter is fully approved | Critical | High | Unit Test | ComiVerse API | TranslatorPaymentService | Bùi Việt Hùng | Đặng Ngọc Thành | Fixed | 2026-08-11 | v1.1.0 | 2026-08-10 | Added final-approval guard before settlement and earning-ledger creation.

## Issues
Issues — Project Issues & Risk Events Log
Issues = problems that have already occurred · Risks = problems that might occur (see Risks sheet) · Category: Technical / Process / Resource / Scope / External
# | Date | Issue Description | Category | Priority | Impact (Scope / Effort / Timeline) | Raised By | Owner | Due Date | Resolution | Status | Closed Date | Notes
I-001 | 2026-06-25 | CORS Policy blocks saving Translator Canvas progress on Vercel frontend. | Technical | High | Delays Translation Workspace integration by 2 days (+2 pts effort). | Bùi Việt Hùng | Bùi Quang Hiệp | Iter 2 | Configured CORS headers correctly on Nginx/Spring Boot security configuration to allow frontend origin. | Closed | 2026-06-27 | Matched DEF-033 in defect register.
I-002 | 2026-07-01 | Revenue split logic failed when multiple translators were assigned to a single chapter task. | Scope | High | Required schema redesign; +3 pts effort. | Lê Thị Tú Kiên | Bùi Việt Hùng | Iter 2 | Changed SRS/DB schema to restrict tasks to 1 assignee. Added Task Handover feature (UC-56) instead. | Closed | 2026-07-04 | Resulted in Change Requests C-002 & C-003.
I-003 | 2026-07-15 | Author chapter upload hangs when ZIP archive contains nested directories. | Technical | Medium | Delays Author publishing module testing by 2 days. | Đặng Ngọc Thành | Đặng Ngọc Thành | Iter 3 | Deprecated strict ZIP upload, implemented webkitdirectory folder upload directly from browser. | Closed | 2026-07-17 | Fixes DEF-005. Recorded as Change C-004.
I-004 | 2026-07-20 | Stripe webhook test events fail in local dev environment, preventing premium checkout testing. | External | High | Blocked Iteration 4 payment testing for 3 days. | Bùi Việt Hùng | Bùi Việt Hùng | Iter 4 | Configured Stripe CLI for local webhook forwarding and added STRIPE_WEBHOOK_SECRET to local .env. | Closed | 2026-07-22 | Standardized local environment setup for all devs.
I-005 | 2026-07-25 | Frontend developer overloaded with both UI integration and E2E testing scripting. | Resource | Medium | High risk of missing L3 System Testing deadline in Iteration 4. | Nguyễn Xuân Hanh | Bùi Quang Hiệp | Iter 4 | Reassigned E2E testing scripts for Admin and Author modules to Ngọc and Thành. Hanh focuses on Reader flows. | Closed | 2026-07-26 | Adjusted task assignments in WBS smoothly.
I-006 | 2026-07-28 | WebSocket sends delayed events causing main thread timeout in Notification Service. | Technical | High | Causes HTTP 500 on triggering APIs; +2 pts effort to fix. | Đặng Ngọc Thành | Đặng Ngọc Thành | Iter 4 | Added @Async annotation to WebSocket dispatch calls to prevent blocking the main thread. | Closed | 2026-07-30 | Fixes DEF-016.

## Risks
Risks — Risk Register & Mitigation Tracking
Probability: High(3) / Medium(2) / Low(1) · Impact: High(3) / Medium(2) / Low(1) · Risk Score = P × I · Score ≥ 6 = Critical; 4-5 = High; 2-3 = Medium; 1 = Low
# | Risk Description | Category | Probability | Impact | Risk Score (P×I) | Mitigation Plan | Contingency Plan | Owner | Due Date | Status | Notes
R-001 | Google OAuth2 API approval delayed / Developer keys expired, blocking user authentication tests | External | 2 | 3 | 6 | Setup Google Cloud Console project early in Iteration 1; use test email accounts | Switch to standard email/password login flow temporarily until keys are approved | Bùi Quang Hiệp | Iter 1 | Closed
R-002 | Key team member unavailable (illness, withdrawal) mid-project | Resource | 1 | 3 | 3 | Cross-train members on critical modules; maintain shared API documentation on Postman | Reassign pending tasks; escalate to Capstone Instructor if unresolvable | Bùi Quang Hiệp | Iter 3 | Open
R-003 | Requirements change after SRS is approved (scope creep from PO/Instructor) | Scope | 2 | 2 | 4 | Strict change control: all changes logged in ChangeLog; no new features mid-iteration | Negotiate scope with PO; defer low-priority nice-to-have features to V2.0 | Bùi Quang Hiệp | Iter 2 | Closed
R-004 | Integration with Stripe Payment Gateway fails in Sandbox environment | Technical | 2 | 2 | 4 | Follow Stripe docs strictly; implement Webhook testing using Stripe CLI locally | Use mocked payment success responses for UAT; document limitation in report | Bùi Việt Hùng | Iter 4 | Closed
R-005 | Performance targets not met (API responds > 3s when querying comics/chapters) | Technical | 1 | 2 | 2 | Add DB indexes (B-Tree/Hash) early; use Redis caching for comic details and views | Scope down concurrent load targets; optimize pagination sizes | Đặng Ngọc Thành | Iter 3 | Open
R-006 | UAT findings require significant UI/UX rework, delaying project defense | Quality | 2 | 3 | 6 | Demo React components to Instructor every 2 weeks; maintain Figma prototypes | Prioritize P1/Critical bug fixes; defer UI cosmetic fixes for post-defense | Chu Tuấn Ngọc | Iter 4 | Open
R-007 | Author chapter upload fails because ZIP file is corrupted, oversized (>50MB), or unsupported | Technical | 2 | 3 | 6 | Validate ZIP structure, file size, and image MIME types before Cloudinary processing | Keep chapter as DRAFT and allow Author to fix the archive and re-upload | Đặng Ngọc Thành | Iter 2 | Closed
R-008 | Cloudinary processing interrupted, causing missing or incorrectly ordered comic pages | Technical | 2 | 3 | 6 | Extract files sequentially, verify page count post-upload, implement Spring @Async rollback | Remove incomplete cloud resources and prompt Author to re-upload | Đặng Ngọc Thành | Iter 2 | Closed
R-009 | Draft, Pending, or Rejected comics/chapters are accidentally leaked to Readers | Quality | 2 | 3 | 6 | Apply PUBLISHED status filtering strictly on all public Reader APIs; write Security tests | Hotfix DB queries immediately; disable affected API routes temporarily | Bùi Quang Hiệp | Iter 3 | Closed
R-010 | Moderator review queue becomes overloaded, causing chapters to remain pending too long | Schedule | 2 | 2 | 4 | Sort Review Queue by submission time; send WebSocket notifications to Moderators | Admins step in to clear backlog; prioritize chapters nearing release deadlines | Bùi Quang Hiệp | Iter 3 | Closed
R-011 | Translation tasks logic fails, causing lost progress in Creator Studio canvas | Quality | 2 | 3 | 6 | Implement Auto-save (Debounce); map text layers strictly to image coordinates | Restore previous saved versions using audit records and translation history | Bùi Việt Hùng | Iter 3 | Closed
R-012 | Monthly Creator payouts (Revenue splits) are duplicated or calculated incorrectly | Financial | 2 | 3 | 6 | Use idempotent settlement jobs; utilize pessimistic DB locking for ledger balance updates | Pause payout batch processing, recalculate manually, and issue adjustment transactions | Bùi Việt Hùng | Iter 4 | Closed
R-013 | Stripe webhook duplicates events, causing users to receive multiple premium unlocks for 1 payment | External | 2 | 3 | 6 | Verify Webhook signatures (HMAC); store unique Stripe event IDs to block duplicates | Suspend user token granting temporarily; manually reconcile Stripe dashboard logs | Bùi Việt Hùng | Iter 4 | Closed
R-014 | Broken RBAC allows Readers or Translators to access Admin/Moderator dashboards | Technical | 2 | 3 | 6 | Enforce @PreAuthorize on Spring controllers; validate JWT claims on React Router guards | Invalidate all active sessions, deploy hotfix to Permission Matrix | Chu Tuấn Ngọc | Iter 3 | Closed
R-015 | Authors upload pirated/copyrighted comics without distribution rights | Compliance | 1 | 3 | 3 | Add reporting feature (UC-26); Moderators can Quarantine suspicious comics instantly | Temporarily hide the disputed comic; Admin investigates and bans violator if proven | Nguyễn Xuân Hanh | Iter 4 | Closed

## ChangeLog
ChangeLog — Requirement & Scope Change Tracking
Log ALL changes to requirements, design, or scope · No mid-sprint changes without approval · Reference this log when versions of SRS/SDS increment
# | Date | Change Description | Requested By | Affects (SRS/WBS/Code) | Impact on Scope | Impact on Effort (pds) | Impact on Timeline | Priority | Approved By | Status | Notes
C-001 | 2026-06-15 | Add 'Forgot Password via OTP' feature to authentication flow | Lê Thị Tú Kiên (Instructor) | SRS v1.0, WBS #3, AuthApi.jsx | Add Reset Password screen and OTP email generation | +3 pts | Delay Iteration 1 by 2 days | High | Lê Thị Tú Kiên | Approved | Essential for user account recovery; integrated via SendGrid.
C-002 | 2026-07-02 | Restrict translation tasks to a single assignee instead of multiple | Bùi Việt Hùng | SRS v1.1, WBS #13, TeamWorkspaceApi.jsx | Remove multi-assignee UI logic; simplify database schema for task assignments | -2 pts | None (Saves effort) | Medium | Bùi Quang Hiệp | Approved | Splitting revenue among multiple translators per task was mathematically unstable. Restricted to 1 person per task.
C-003 | 2026-07-18 | Add 'Task Handover' feature (UC-56) for translation teams | Lê Thị Tú Kiên / Bùi Việt Hùng | SRS v1.1, WBS #13, ProjectTeamApi.jsx | Add UI for Project Leaders to reassign incomplete tasks while preserving partial revenue splits | +5 pts | Delay Iteration 3 by 3 days | High | Lê Thị Tú Kiên | Approved | Addressed an incident where translators dropped out mid-chapter, blocking project completion.
C-004 | 2026-07-28 | Upgrade Chapter Upload to support direct Folder uploads (deprecated strict .zip/.cbz) | Đặng Ngọc Thành | SRS v1.1, WBS #10, chapterFolderUpload.js | Rewrite upload component to use webkitdirectory, parsing relative paths directly in browser | +6 pts | Delay Iteration 3 by 2 days | High | Bùi Quang Hiệp | Approved | Authors had issues packaging correct ZIP structures. Direct folder upload greatly improves UX.
C-005 | 2026-08-01 | Replace HTTP polling with STOMP WebSockets for Community Chat | Nguyễn Xuân Hanh | Architecture, WBS #9, StompService.js | Implement STOMP client; configure Spring Boot WebSocket message broker | +4 pts | Absorbed within Iteration 4 buffer | Medium | Bùi Quang Hiệp | Approved | HTTP polling was overloading the server and causing 429 Rate Limit errors.